## Cost Breakdown
LINE ITEM | BUDGET | Prev. Invoiced | CURRENT INVOICE | TOTAL INVOICED | TO BE COMPLETED | OVER BUDGET | CHANGE ORDERS
DESIGN SERVICES
Plan Desgin | 17850 |  | 9246.3 | 9246.3 | 8603.7 | 0 | 0
Plan Printing & Photocopying | 525 |  | 158.93 | 158.93 | 366.07 | 0 | 0
DESIGN SERVICES — Subtotal | 18375 | 0 | 9405.23 | 9405.23 | 8969.77 | 0 | 0
PERMITS & HOME WARRANTY
Building Permit Fees | 10500 |  | 8216.35 | 8216.35 | 2283.65 | 0 | 0
Home Warranty Registration & Fees | 2100 |  | 1250 | 1250 | 850 | 0 | 0
BC Housing Registration Fee | 42 |  | 40 | 40 | 2 | 0 | 0
DCC Fees | 10500 |  | 0 | 0 | 10500 | 0 | 0
PERMITS & HOME WARRANTY — Subtotal | 23142 | 0 | 9506.35 | 9506.35 | 13635.65 | 0 | 0
ENGINEERING FEES
Energy Advisor | 1575 |  | 918.75 | 918.75 | 656.25 | 0 | 0
Land Survey | 8400 |  | 8035.13 | 8035.13 | 364.87 | 0 | 0
Geotechnical Engineering | 2100 |  | 883.68 | 883.68 | 1216.32 | 0 | 0
Structural Engineering | 7350 |  | 7849.17 | 7849.17 | 0 | -499.17 | 0
ENGINEERING FEES — Subtotal | 19425 | 0 | 17686.73 | 17686.73 | 2237.44 | -499.17 | 0
SITE WORK
Backfill, Perimeter & Drain Material | 21000 |  | 25071.19 | 25071.19 | 0 | -4071.19 | 0
Excavation, Backfill, Perimeter & Drain Labour | 21000 |  | 59319.02 | 59319.02 | 0 | -38319.02 | 0
Septic | 26250 |  | 1795.5 | 1795.5 | 24454.5 | 0 | 0
SITE WORK — Subtotal | 68250 | 0 | 86185.71 | 86185.71 | 24454.5 | -42390.21 | 0
FOUNDATION
Footings and Foundation Material | 8597.5365 |  | 16250.66 | 16250.66 | 0 | -7653.1235 | 0
Foundation & Footings concrete | 28140 |  | 23549.78 | 23549.78 | 4590.22 | 0 | 0
Footings & Foundation Labor | 13649.3805 |  | 15750 | 15750 | 0 | -2100.6195 | 0
Slab Prep - Material | 435.372 |  | 0 | 0 | 435.372 | 0 | 0
Garage Concrete Slab | 5040 |  | 4074.01 | 4074.01 | 965.99 | 0 | 0
Concrete Skim Coat Materials | 6300 |  | 5354.94 | 5354.94 | 945.06 | 0 | 0
Garage Concrete Slab Finishing Labor | 3620.925 |  | 0 | 0 | 3620.925 | 0 | 0
Concrete Pump Truck | 3780 |  | 3664.42 | 3664.42 | 115.58 | 0 | 0
Damproofing | 10500 |  | 3379.95 | 3379.95 | 7120.05 | 0 | 0
FOUNDATION — Subtotal | 80063.214 | 0 | 72023.76 | 72023.76 | 17793.197 | -9753.743 | 0
FRAMING
Framing Materials Cost | 41235.0855 |  | 59647.01 | 59647.01 | 0 | -18411.9245 | 0
Roof Trusses | 45150 |  | 43603.7 | 43603.7 | 1546.3 | 0 | 0
Floor System | 14275.6845 |  | 12383 | 12383 | 1892.6845 | 0 | 0
Engineering Hardware | 11718.2205 |  | 0 | 0 | 11718.2205 | 0 | 0
Extra | 5250 |  | 0 | 0 | 5250 | 0 | 0
FRAMING — Subtotal | 117628.9905 | 0 | 115633.71 | 115633.71 | 20407.205 | -18411.9245 | 0
WINDOWS
Windows | 32873.736 |  | 25812.63 | 25812.63 | 7061.106 | 0 | 0
Blinds | 6300 |  | 0 | 0 | 6300 | 0 | 0
WINDOWS — Subtotal | 39173.736 | 0 | 25812.63 | 25812.63 | 13361.106 | 0 | 0
DOORS
Exterior Doors | 9450 |  | 5894.34 | 5894.34 | 3555.66 | 0 | 0
Interior Doors | 5250 |  | 265.98 | 265.98 | 4984.02 | 0 | 0
Garage Doors | 20250.4155 |  | 0 | 0 | 20250.4155 | 0 | 0
Door Hardware | 1575 |  | 0 | 0 | 1575 | 0 | 0
Sliding Door | 16168.509 |  | 15118.53 | 15118.53 | 1049.979 | 0 | 0
DOORS — Subtotal | 52693.9245 | 0 | 21278.85 | 21278.85 | 31415.0745 | 0 | 0
ELECTRICAL
Electrical Rough In & Finish | 70733.25 |  | 55228.71 | 55228.71 | 15504.54 | 0 | 0
Electrical Rough In & Finish - Change Order | 0 |  | 7333.67 | 7333.67 | 0 | 0 | 7333.67
Electrical Fixtures | 1050 |  | 0 | 0 | 1050 | 0 | 0
BC Hydro | 3675 |  | 4887.75 | 4887.75 | 0 | -1212.75 | 0
ELECTRICAL — Subtotal | 75458.25 | 0 | 67450.13 | 67450.13 | 16554.54 | -1212.75 | 7333.67
PLUMBING
Plumbing Rough In & Finish | 26250 |  | 29427.32 | 29427.32 | 0 | -3177.32 | 0
PLUMBING — Subtotal | 26250 | 0 | 29427.32 | 29427.32 | 0 | -3177.32 | 0
HVAC
Mechanical Rough In & Finish | 56852.25 |  | 29581.13 | 29581.13 | 27271.12 | 0 | 0
NAVIEN ON DEMAND | 4688.25 |  | 0 | 0 | 4688.25 | 0 | 0
NAPOLEON GAS FIRE PLACE | 3517.5 |  | 0 | 0 | 3517.5 | 0 | 0
GAS LINES | 577.5 |  | 0 | 0 | 577.5 | 0 | 0
Gas/Propane Connection | 577.5 |  | 0 | 0 | 577.5 | 0 | 0
HVAC — Subtotal | 66213 | 0 | 29581.13 | 29581.13 | 36631.87 | 0 | 0
ROOFING
Roofing Supply & Install | 34545 |  | 22687.23 | 22687.23 | 11857.77 | 0 | 0
ROOFING — Subtotal | 34545 | 0 | 22687.23 | 22687.23 | 11857.77 | 0 | 0
INSULATION & DRYWALL
Insulation | 38921.7045 |  | 0 | 0 | 38921.7045 | 0 | 0
Drywall | 50539.8915 |  | 89461.6 | 89461.6 | 0 | -38921.7085 | 0
INSULATION & DRYWALL — Subtotal | 89461.596 | 0 | 89461.6 | 89461.6 | 38921.7045 | -38921.7085 | 0
EXTERIOR VENEER
Siding Materials | 18640.041 |  | 14171.96 | 14171.96 | 4468.081 | 0 | 0
Soffit Supply & Install | 15093.75 |  | 0 | 0 | 15093.75 | 0 | 0
Gutters Supply & Install | 5307.75 |  | 0 | 0 | 5307.75 | 0 | 0
Trim Labour | 6699 |  | 0 | 0 | 6699 | 0 | 0
Cedar Soffit | 6023.2095 |  | 0 | 0 | 6023.2095 | 0 | 0
Stucco | 21000 |  | 0 | 0 | 21000 | 0 | 0
EXTERIOR VENEER — Subtotal | 72763.7505 | 0 | 14171.96 | 14171.96 | 58591.7905 | 0 | 0
MASONRY
Stone Fireplace | 15750 |  | 0 | 0 | 15750 | 0 | 0
MASONRY — Subtotal | 15750 | 0 | 0 | 0 | 15750 | 0 | 0
CABINETRY & COUNTERTOPS
Cabinetry Supply & Install | 52500 |  | 0 | 0 | 52500 | 0 | 0
Countertop Supply & Install | 22974 |  | 0 | 0 | 22974 | 0 | 0
CABINETRY & COUNTERTOPS — Subtotal | 75474 | 0 | 0 | 0 | 75474 | 0 | 0
INTERIOR FINISHING
Finishing Carpentry | 4200 |  | 0 | 0 | 4200 | 0 | 0
Interior Trim Materials | 4488.876 |  | 0 | 0 | 4488.876 | 0 | 0
Closet Shelving | 5250 |  | 0 | 0 | 5250 | 0 | 0
Bathroom Hardware | 1050 |  | 0 | 0 | 1050 | 0 | 0
Shower Glass Doors | 4200 |  | 0 | 0 | 4200 | 0 | 0
Mirrors | 1050 |  | 0 | 0 | 1050 | 0 | 0
INTERIOR FINISHING — Subtotal | 20238.876 | 0 | 0 | 0 | 20238.876 | 0 | 0
WOOD FLOOR COVERINGS
Flooring Material | 12505.5 |  | 0 | 0 | 12505.5 | 0 | 0
Flooring Install Labour | 12505.5 |  | 0 | 0 | 12505.5 | 0 | 0
Floor Sanding & Prep / Self living | 3150 |  | 0 | 0 | 3150 | 0 | 0
Protective Floor Covering | 15750 |  | 0 | 0 | 15750 | 0 | 0
Custom Stair Nosings | 840 |  | 0 | 0 | 840 | 0 | 0
WOOD FLOOR COVERINGS — Subtotal | 44751 | 0 | 0 | 0 | 44751 | 0 | 0
TILE
Floor Tile Material | 3640.14 |  | 0 | 0 | 3640.14 | 0 | 0
Floor Tie Install Labour | 4536 |  | 0 | 0 | 4536 | 0 | 0
Wall Tile Prep | 1568.7 |  | 0 | 0 | 1568.7 | 0 | 0
Wall Tile Material | 3357.018 |  | 0 | 0 | 3357.018 | 0 | 0
Wall Tile Labour | 6274.8 |  | 0 | 0 | 6274.8 | 0 | 0
Backsplash Tile Material | 1348.2 |  | 0 | 0 | 1348.2 | 0 | 0
Backsplash Tile Labour | 840 |  | 0 | 0 | 840 | 0 | 0
Heated Floor Prep | 2604 |  | 0 | 0 | 2604 | 0 | 0
Heated floor Thermostat | 640.941 |  | 0 | 0 | 640.941 | 0 | 0
Heated Floor Cables | 1106.616 |  | 0 | 0 | 1106.616 | 0 | 0
Custom Niche | 3465 |  | 0 | 0 | 3465 | 0 | 0
Schluter Trim | 157.5 |  | 0 | 0 | 157.5 | 0 | 0
TILE — Subtotal | 29538.915 | 0 | 0 | 0 | 29538.915 | 0 | 0
PAINT
Interior & Exterior Paint | 36750 |  | 42.09 | 42.09 | 36707.91 | 0 | 0
PAINT — Subtotal | 36750 | 0 | 42.09 | 42.09 | 36707.91 | 0 | 0
EXTERIOR HARDSCAPE
Patio/Drives/Walkways Concrete & Material | 12600 |  | 16.12 | 16.12 | 12583.88 | 0 | 0
Patio/Drives/Walkways Finishing Labour | 6300 |  | 0 | 0 | 6300 | 0 | 0
Retaining Walls Concrete & Material | 5250 |  | 0 | 0 | 5250 | 0 | 0
Landscaping | 31500 |  | 0 | 0 | 31500 | 0 | 0
EXTERIOR HARDSCAPE — Subtotal | 55650 | 0 | 16.12 | 16.12 | 55633.88 | 0 | 0
CONSTRUCTION CLEAN UP
Disposal & Dump Fees | 2625 |  | 3138.63 | 3138.63 | 0 | -513.63 | 0
Dumpster Rental | 2625 |  | 0 | 0 | 2625 | 0 | 0
Final Site Clean | 2625 |  | 0 | 0 | 2625 | 0 | 0
CONSTRUCTION CLEAN UP — Subtotal | 7875 | 0 | 3138.63 | 3138.63 | 5250 | -513.63 | 0
RENTAL& JOBSITE FACILITIES
Portable Toilet | 2136.75 |  | 668.53 | 668.53 | 1468.22 | 0 | 0
Specialty Tool & Equipment Rental | 2625 |  | 2748.73 | 2748.73 | 0 | -123.73 | 0
RENTAL& JOBSITE FACILITIES— Subtotal | 4761.75 | 0 | 3417.26 | 3417.26 | 1468.22 | -123.73 | 0
MISCELLANEOUS
Appliances | 26250 |  | 0 | 0 | 26250 | 0 | 0
Appraisal | 2625 |  | 0 | 0 | 2625 | 0 | 0
Insurance | 5250 |  | 4450 | 4450 | 800 | 0 | 0
Lawyer Fees | 6300 |  | 0 | 0 | 6300 | 0 | 0
Interest | 31500 |  | 0 | 0 | 31500 | 0 | 0
Transfer Tax | 12600 |  | 0 | 0 | 12600 | 0 | 0
Furniture | 15750 |  | 0 | 0 | 15750 | 0 | 0
MISCELLANEOUS — Subtotal | 100275 | 0 | 4450 | 4450 | 95825 | 0 | 0
Mcmann Labour Site work - Foundation- Framing- Siding - Finishing
Seth | 7980 |  | 5490.45 | 5490.45 | 2489.55 | 0 | 0
Aaron | 6300 |  | 6403.17 | 6403.17 | 0 | -103.17 | 0
Alaa & Jason | 8400 |  | 4813.89 | 4813.89 | 3586.11 | 0 | 0
James / Abdul & Kevin | 9030 |  | 4340.89 | 4340.89 | 4689.11 | 0 | 0
Fielding | 13104 |  | 16060.02 | 16060.02 | 0 | -2956.02 | 0
Other - Alex & Joel & Kyle | 7295.4 |  | 7772.42 | 7772.42 | 0 | -477.02 | 0
Mcmann Labour — Subtotal | 52109.4 | 0 | 44880.84 | 44880.84 | 10764.77 | -3536.21 | 0
PROJECT TOTAL | 1226617.4025 | 0 | 666257.28 | 666257.28 | 686234.1885 | -118540.396 | 7333.67

## Timesheet
LINE ITEM | Date | Name | Billing Status | Duration
04 Site Work:Excavation,Backfill,Perimeter &
| 2026-02-17 | Fielding K Benton | Unbilled | 4
| 2026-02-17 | Fielding K Benton | Unbilled | 4
| 2026-02-18 | Fielding K Benton | Unbilled | 4.5
| 2026-02-18 | Fielding K Benton | Unbilled | 0.67
| 2026-02-19 | Fielding K Benton | Unbilled | 2.17
| 2026-02-19 | Fielding K Benton | Unbilled | 0.33
| 2026-02-20 | Fielding K Benton | Unbilled | 3.83
| 2026-02-23 | Fielding K Benton | Unbilled | 0.5
| 2026-02-27 | Fielding K Benton | Unbilled | 5.17
| 2026-02-27 | Fielding K Benton | Unbilled | 2.83
| 2026-03-02 | Fielding K Benton | Unbilled | 3.5
| 2026-03-03 | Fielding K Benton | Unbilled | 0.83
| 2026-03-03 | Fielding K Benton | Unbilled | 0.83
| 2026-03-04 | Fielding K Benton | Unbilled | 2.67
| 2026-03-04 | Fielding K Benton | Unbilled | 0
| 2026-03-04 | Fielding K Benton | Unbilled | 3.5
| 2026-03-05 | Fielding K Benton | Unbilled | 4.33
| 2026-03-05 | Fielding K Benton | Unbilled | 4.5
| 2026-03-06 | Fielding K Benton | Unbilled | 1.83
| 2026-03-06 | Fielding K Benton | Unbilled | 2.25
| 2026-03-06 | Fielding K Benton | Unbilled | 3.67
| 2026-03-06 | Fielding K Benton | Unbilled | 0.33
Total 04 Site Work:Excavation,Backfill,Perimeter & |  |  |  | 56.24
05 Foundation:Footings & Foundation Labor
| 2026-02-23 | Fielding K Benton | Unbilled | 3.83
| 2026-02-23 | Fielding K Benton | Unbilled | 0.5
| 2026-02-24 | Fielding K Benton | Unbilled | 4.17
| 2026-02-25 | Fielding K Benton | Unbilled | 0.17
| 2026-02-25 | Fielding K Benton | Unbilled | 2.33
| 2026-02-26 | Alaa Kadah | Unbilled | 3.67
| 2026-03-02 | Fielding K Benton | Unbilled | 2.67
| 2026-03-09 | Alaa Kadah | Unbilled | 2.83
| 2026-03-09 | Alaa Kadah | Unbilled | 4.17
| 2026-03-09 | Fielding K Benton | Unbilled | 6.17
| 2026-03-09 | Fielding K Benton | Unbilled | 2.83
| 2026-03-10 | Alaa Kadah | Unbilled | 4
| 2026-03-10 | Alaa Kadah | Unbilled | 0
| 2026-03-10 | Alaa Kadah | Unbilled | 3.5
| 2026-03-10 | Fielding K Benton | Unbilled | 5.5
| 2026-03-10 | Fielding K Benton | Unbilled | 2.83
| 2026-03-11 | Alaa Kadah | Unbilled | 0.33
| 2026-03-11 | Fielding K Benton | Unbilled | 6.67
| 2026-03-11 | Fielding K Benton | Unbilled | 0.5
| 2026-03-11 | Fielding K Benton | Unbilled | 0.17
| 2026-03-12 | Fielding K Benton | Unbilled | 3.17
| 2026-03-12 | Fielding K Benton | Unbilled | 2.17
| 2026-03-12 | Fielding K Benton | Unbilled | 2.17
| 2026-03-13 | Aaron Maskill | Unbilled | 2
| 2026-03-13 | Aaron Maskill | Unbilled | 1
| 2026-03-13 | Alaa Kadah | Unbilled | 3.17
| 2026-03-13 | Fielding K Benton | Unbilled | 6
| 2026-03-16 | Fielding K Benton | Unbilled | 5.17
| 2026-03-16 | Fielding K Benton | Unbilled | 2.83
| 2026-03-18 | Fielding K Benton | Unbilled | 1.42
| 2026-03-20 | Fielding K Benton | Unbilled | 1.33
| 2026-03-20 | Fielding K Benton | Unbilled | 3.17
Total 05 Foundation:Footings & Foundation Labor |  |  |  | 90.44
05 Foundation:Slap Prep Labor
| 2026-06-25 | Fielding K Benton | Unbilled | 1.25
| 2026-06-25 | Fielding K Benton | Unbilled | 1.67
| 2026-06-30 | Fielding K Benton | Unbilled | 0.17
Total 05 Foundation:Slap Prep Labor |  |  |  | 3.09
06 Framing:Framing Labor
| 2026-03-23 | Aaron Maskill | Unbilled | 4
| 2026-03-23 | Aaron Maskill | Unbilled | 3.75
| 2026-03-23 | Fielding K Benton | Unbilled | 0.75
| 2026-03-23 | Fielding K Benton | Unbilled | 3.42
| 2026-03-25 | Aaron Maskill | Unbilled | 4.25
| 2026-03-25 | Aaron Maskill | Unbilled | 0
| 2026-03-25 | Aaron Maskill | Unbilled | 5.58
| 2026-03-25 | Fielding K Benton | Unbilled | 2.58
| 2026-03-25 | Fielding K Benton | Unbilled | 3.25
| 2026-03-26 | Aaron Maskill | Unbilled | 4.25
| 2026-03-26 | Aaron Maskill | Unbilled | 3.08
| 2026-03-26 | Fielding K Benton | Unbilled | 5.33
| 2026-03-26 | Fielding K Benton | Unbilled | 2.75
| 2026-03-27 | Aaron Maskill | Unbilled | 1.58
| 2026-03-27 | Fielding K Benton | Unbilled | 1.83
| 2026-03-27 | Seth Bibbs | Unbilled | 0.33
| 2026-03-30 | Aaron Maskill | Unbilled | 5
| 2026-03-30 | Aaron Maskill | Unbilled | 3.25
| 2026-03-30 | Fielding K Benton | Unbilled | 4.58
| 2026-03-30 | Fielding K Benton | Unbilled | 3.33
| 2026-03-31 | Aaron Maskill | Unbilled | 4.67
| 2026-03-31 | Aaron Maskill | Unbilled | 4.5
| 2026-03-31 | Fielding K Benton | Unbilled | 4.67
| 2026-03-31 | Fielding K Benton | Unbilled | 4.33
| 2026-04-01 | Aaron Maskill | Unbilled | 3.25
| 2026-04-01 | Aaron Maskill | Unbilled | 1.33
| 2026-04-02 | Aaron Maskill | Unbilled | 4.42
| 2026-04-02 | Aaron Maskill | Unbilled | 3.5
| 2026-04-02 | Fielding K Benton | Unbilled | 4.58
| 2026-04-02 | Fielding K Benton | Unbilled | 4.17
| 2026-04-06 | Aaron Maskill | Unbilled | 5.08
| 2026-04-06 | Aaron Maskill | Unbilled | 4.83
| 2026-04-06 | Fielding K Benton | Unbilled | 5.08
| 2026-04-06 | Fielding K Benton | Unbilled | 4.83
| 2026-04-07 | Aaron Maskill | Unbilled | 5.25
| 2026-04-07 | Aaron Maskill | Unbilled | 4.75
| 2026-04-07 | Alaa Kadah | Unbilled | 4.92
| 2026-04-07 | Alaa Kadah | Unbilled | 4.67
| 2026-04-07 | Fielding K Benton | Unbilled | 5.17
| 2026-04-07 | Fielding K Benton | Unbilled | 4.83
| 2026-04-08 | Aaron Maskill | Unbilled | 5.83
| 2026-04-08 | Aaron Maskill | Unbilled | 4.17
| 2026-04-08 | Aaron Maskill | Unbilled | 0.17
| 2026-04-08 | Alaa Kadah | Unbilled | 0.83
| 2026-04-08 | Alaa Kadah | Unbilled | 4.08
| 2026-04-08 | Alaa Kadah | Unbilled | 0.25
| 2026-04-08 | Fielding K Benton | Unbilled | 1.08
| 2026-04-08 | Fielding K Benton | Unbilled | 0.25
| 2026-04-09 | Aaron Maskill | Unbilled | 5.92
| 2026-04-09 | Aaron Maskill | Unbilled | 3.5
| 2026-04-09 | Fielding K Benton | Unbilled | 6.08
| 2026-04-09 | Fielding K Benton | Unbilled | 3.5
| 2026-04-13 | Aaron Maskill | Unbilled | 6
| 2026-04-13 | Aaron Maskill | Unbilled | 4
| 2026-04-13 | Alaa Kadah | Unbilled | 5.75
| 2026-04-13 | Alaa Kadah | Unbilled | 3.83
| 2026-04-13 | Fielding K Benton | Unbilled | 6.17
| 2026-04-13 | Fielding K Benton | Unbilled | 3.83
| 2026-04-13 | Fielding K Benton | Unbilled | 0.17
| 2026-04-13 | Seth Bibbs | Unbilled | 1.75
| 2026-04-13 | Seth Bibbs | Unbilled | 0.08
| 2026-04-14 | Aaron Maskill | Unbilled | 4.58
| 2026-04-14 | Aaron Maskill | Unbilled | 5
| 2026-04-14 | Fielding K Benton | Unbilled | 4.67
| 2026-04-14 | Fielding K Benton | Unbilled | 5
| 2026-04-14 | Seth Bibbs | Unbilled | 5.75
| 2026-04-14 | Seth Bibbs | Unbilled | 0.42
| 2026-04-15 | Aaron Maskill | Unbilled | 5.33
| 2026-04-15 | Aaron Maskill | Unbilled | 4.25
| 2026-04-15 | Fielding K Benton | Unbilled | 4.83
| 2026-04-15 | Fielding K Benton | Unbilled | 4.75
| 2026-04-15 | Seth Bibbs | Unbilled | 5.58
| 2026-04-15 | Seth Bibbs | Unbilled | 4.25
| 2026-04-16 | Aaron Maskill | Unbilled | 6.67
| 2026-04-16 | Aaron Maskill | Unbilled | 3.33
| 2026-04-16 | Aaron Maskill | Unbilled | 0.25
| 2026-04-16 | Fielding K Benton | Unbilled | 6.17
| 2026-04-16 | Fielding K Benton | Unbilled | 3.83
| 2026-04-16 | Fielding K Benton | Unbilled | 0.42
| 2026-04-16 | Seth Bibbs | Unbilled | 6.25
| 2026-04-16 | Seth Bibbs | Unbilled | 3.75
| 2026-04-20 | Aaron Maskill | Unbilled | 6.17
| 2026-04-20 | Aaron Maskill | Unbilled | 3.58
| 2026-04-20 | Fielding K Benton | Unbilled | 6
| 2026-04-20 | Fielding K Benton | Unbilled | 0.67
| 2026-04-20 | Seth Bibbs | Unbilled | 6.08
| 2026-04-21 | Fielding K Benton | Unbilled | 0.25
| 2026-05-04 | Fielding K Benton | Unbilled | 5.17
| 2026-05-04 | Fielding K Benton | Unbilled | 3.33
| 2026-05-05 | Fielding K Benton | Unbilled | 10
| 2026-05-05 | Fielding K Benton | Unbilled | 0.33
| 2026-05-06 | Fielding K Benton | Unbilled | 5.08
| 2026-05-06 | Fielding K Benton | Unbilled | 3.75
| 2026-05-07 | Fielding K Benton | Unbilled | 7.67
| 2026-05-07 | James McMann | Unbilled | 8.08
| 2026-05-08 | Jason A Kirstein | Unbilled | 3.25
| 2026-05-08 | Jason A Kirstein | Unbilled | 1.75
| 2026-05-11 | Fielding K Benton | Unbilled | 6
| 2026-05-11 | Fielding K Benton | Unbilled | 4
| 2026-05-11 | Fielding K Benton | Unbilled | 1.17
| 2026-05-12 | Fielding K Benton | Unbilled | 5.17
| 2026-05-12 | Fielding K Benton | Unbilled | 4.83
| 2026-05-12 | Fielding K Benton | Unbilled | 1.17
| 2026-05-12 | Jason A Kirstein | Unbilled | 1.75
| 2026-05-13 | Aaron Maskill | Unbilled | 5.67
| 2026-05-13 | Aaron Maskill | Unbilled | 4.33
| 2026-05-13 | Aaron Maskill | Unbilled | 0.08
| 2026-05-13 | Fielding K Benton | Unbilled | 5.08
| 2026-05-13 | Fielding K Benton | Unbilled | 4.58
| 2026-05-13 | Jason A Kirstein | Unbilled | 5.67
| 2026-05-13 | Jason A Kirstein | Unbilled | 4.17
| 2026-05-14 | Aaron Maskill | Unbilled | 5.33
| 2026-05-14 | Aaron Maskill | Unbilled | 4.58
| 2026-05-14 | Fielding K Benton | Unbilled | 9.67
| 2026-05-14 | Jason A Kirstein | Unbilled | 5.33
| 2026-05-14 | Jason A Kirstein | Unbilled | 4.67
| 2026-05-14 | Jason A Kirstein | Unbilled | 0.08
| 2026-05-19 | Fielding K Benton | Unbilled | 5.33
| 2026-05-19 | Fielding K Benton | Unbilled | 4.67
| 2026-05-19 | Fielding K Benton | Unbilled | 0.25
| 2026-05-19 | Jason A Kirstein | Unbilled | 5.17
| 2026-05-19 | Jason A Kirstein | Unbilled | 4.83
| 2026-05-19 | Jason A Kirstein | Unbilled | 0.08
| 2026-05-20 | Aaron Maskill | Unbilled | 6.08
| 2026-05-20 | Aaron Maskill | Unbilled | 3.92
| 2026-05-20 | Aaron Maskill | Unbilled | 0.42
| 2026-05-20 | Fielding K Benton | Unbilled | 6.08
| 2026-05-20 | Fielding K Benton | Unbilled | 1
| 2026-05-20 | Fielding K Benton | Unbilled | 1.5
| 2026-05-20 | Fielding K Benton | Unbilled | 0.33
| 2026-05-20 | Jason A Kirstein | Unbilled | 5.92
| 2026-05-20 | Jason A Kirstein | Unbilled | 1.42
| 2026-05-20 | Jason A Kirstein | Unbilled | 1.67
| 2026-05-20 | Jason A Kirstein | Unbilled | 0.08
| 2026-05-21 | Fielding K Benton | Unbilled | 6.58
| 2026-05-21 | Fielding K Benton | Unbilled | 1.25
| 2026-05-21 | Fielding K Benton | Unbilled | 0.17
| 2026-05-21 | Jason A Kirstein | Unbilled | 5.92
| 2026-05-21 | Jason A Kirstein | Unbilled | 4.08
| 2026-05-21 | Jason A Kirstein | Unbilled | 0.25
| 2026-05-22 | Aaron Maskill | Unbilled | 2.83
| 2026-05-22 | Aaron Maskill | Unbilled | 2
| 2026-05-22 | Alexander D Gazzola | Unbilled | 3.92
| 2026-05-22 | Alexander D Gazzola | Unbilled | 0
| 2026-05-25 | Jason A Kirstein | Unbilled | 5.42
| 2026-05-25 | Jason A Kirstein | Unbilled | 4.58
| 2026-05-25 | Alexander D Gazzola | Unbilled | 6.08
| 2026-05-25 | Alexander D Gazzola | Unbilled | 3.92
| 2026-05-25 | Alexander D Gazzola | Unbilled | 0.42
| 2026-05-25 | Fielding K Benton | Unbilled | 5.42
| 2026-05-25 | Fielding K Benton | Unbilled | 4.58
| 2026-05-25 | Fielding K Benton | Unbilled | 0.42
| 2026-05-26 | Jason A Kirstein | Unbilled | 5.33
| 2026-05-26 | Jason A Kirstein | Unbilled | 4.67
| 2026-05-26 | Jason A Kirstein | Unbilled | 0.25
| 2026-05-26 | Alexander D Gazzola | Unbilled | 5.58
| 2026-05-26 | Alexander D Gazzola | Unbilled | 4.33
| 2026-05-26 | Fielding K Benton | Unbilled | 1
| 2026-05-26 | Fielding K Benton | Unbilled | 4.08
| 2026-05-26 | Fielding K Benton | Unbilled | 4.33
| 2026-05-26 | Fielding K Benton | Unbilled | 0.08
| 2026-05-26 | James McMann | Unbilled | 4.75
| 2026-05-26 | James McMann | Unbilled | 1.75
| 2026-05-26 | Seth Bibbs | Unbilled | 5.67
| 2026-05-26 | Seth Bibbs | Unbilled | 4.08
| 2026-05-27 | Jason A Kirstein | Unbilled | 5.75
| 2026-05-27 | Jason A Kirstein | Unbilled | 4.25
| 2026-05-27 | Jason A Kirstein | Unbilled | 0.08
| 2026-05-27 | Alexander D Gazzola | Unbilled | 6.17
| 2026-05-27 | Alexander D Gazzola | Unbilled | 3.83
| 2026-05-27 | Alexander D Gazzola | Unbilled | 0.17
| 2026-05-27 | Fielding K Benton | Unbilled | 3.08
| 2026-05-27 | Fielding K Benton | Unbilled | 2.92
| 2026-05-27 | Fielding K Benton | Unbilled | 4
| 2026-05-27 | Fielding K Benton | Unbilled | 0.17
| 2026-05-27 | James McMann | Unbilled | 2.25
| 2026-05-27 | Seth Bibbs | Unbilled | 6.17
| 2026-05-27 | Seth Bibbs | Unbilled | 3.83
| 2026-05-27 | Seth Bibbs | Unbilled | 0.08
| 2026-05-28 | Jason A Kirstein | Unbilled | 1.42
| 2026-05-28 | Alexander D Gazzola | Unbilled | 5.83
| 2026-05-28 | Alexander D Gazzola | Unbilled | 3.92
| 2026-05-28 | Fielding K Benton | Unbilled | 6.25
| 2026-05-28 | Fielding K Benton | Unbilled | 3.75
| 2026-05-28 | Seth Bibbs | Unbilled | 5.33
| 2026-05-28 | Seth Bibbs | Unbilled | 4.17
| 2026-05-29 | Alexander D Gazzola | Unbilled | 0.33
| 2026-05-29 | Alexander D Gazzola | Unbilled | 5.08
| 2026-05-29 | Alexander D Gazzola | Unbilled | 4.08
| 2026-06-01 | Alexander D Gazzola | Unbilled | 5.83
| 2026-06-01 | Alexander D Gazzola | Unbilled | 0
| 2026-06-01 | Alexander D Gazzola | Unbilled | 4.17
| 2026-06-01 | Alexander D Gazzola | Unbilled | 0.08
| 2026-06-01 | Jason A Kirstein | Unbilled | 5.75
| 2026-06-01 | Jason A Kirstein | Unbilled | 0.5
| 2026-06-01 | Jason A Kirstein | Unbilled | 0.75
| 2026-06-01 | Jason A Kirstein | Unbilled | 0.08
| 2026-06-01 | Seth Bibbs | Unbilled | 5.42
| 2026-06-01 | Seth Bibbs | Unbilled | 4.58
| 2026-06-02 | Alexander D Gazzola | Unbilled | 5.58
| 2026-06-02 | Alexander D Gazzola | Unbilled | 4.42
| 2026-06-02 | Alexander D Gazzola | Unbilled | 0.25
| 2026-06-02 | Alexander D Gazzola | Unbilled | 0
| 2026-06-02 | Fielding K Benton | Unbilled | 5.42
| 2026-06-02 | Fielding K Benton | Unbilled | 4.58
| 2026-06-02 | Fielding K Benton | Unbilled | 0.42
| 2026-06-02 | Seth Bibbs | Unbilled | 5.5
| 2026-06-02 | Seth Bibbs | Unbilled | 3.58
| 2026-06-03 | Alexander D Gazzola | Unbilled | 5.58
| 2026-06-03 | Alexander D Gazzola | Unbilled | 4.42
| 2026-06-03 | Fielding K Benton | Unbilled | 6.08
| 2026-06-03 | Fielding K Benton | Unbilled | 3.92
| 2026-06-03 | Fielding K Benton | Unbilled | 0.17
| 2026-06-03 | Seth Bibbs | Unbilled | 5.42
| 2026-06-03 | Seth Bibbs | Unbilled | 4.25
| 2026-06-04 | Alexander D Gazzola | Unbilled | 10
| 2026-06-04 | Alexander D Gazzola | Unbilled | 0.25
| 2026-06-04 | Fielding K Benton | Unbilled | 10
| 2026-06-04 | Fielding K Benton | Unbilled | 0.58
| 2026-06-04 | Seth Bibbs | Unbilled | 5.33
| 2026-06-04 | Seth Bibbs | Unbilled | 4.42
| 2026-06-05 | Alexander D Gazzola | Unbilled | 10
| 2026-06-05 | Alexander D Gazzola | Unbilled | 0.58
| 2026-06-06 | Alexander D Gazzola | Unbilled | 9.58
| 2026-06-08 | Seth Bibbs | Unbilled | 5.92
| 2026-06-08 | Seth Bibbs | Unbilled | 0
| 2026-06-08 | Seth Bibbs | Unbilled | 3.83
| 2026-06-09 | Alexander D Gazzola | Unbilled | 7.75
| 2026-06-09 | Fielding K Benton | Unbilled | 5.92
| 2026-06-09 | Fielding K Benton | Unbilled | 4.08
| 2026-06-09 | Fielding K Benton | Unbilled | 0.08
| 2026-06-10 | Fielding K Benton | Unbilled | 10
| 2026-06-10 | Fielding K Benton | Unbilled | 0.08
| 2026-06-11 | Fielding K Benton | Unbilled | 7.58
| 2026-06-11 | Fielding K Benton | Unbilled | 0.42
| 2026-06-11 | Seth Bibbs | Unbilled | 1.17
| 2026-06-12 | Alexander D Gazzola | Unbilled | 4.92
| 2026-06-12 | Alexander D Gazzola | Unbilled | 1.17
| 2026-06-12 | Seth Bibbs | Unbilled | 0.75
| 2026-06-14 | Fielding K Benton | Unbilled | 0.42
| 2026-06-15 | Alexander D Gazzola | Unbilled | 5.92
| 2026-06-15 | Alexander D Gazzola | Unbilled | 4.08
| 2026-06-15 | Fielding K Benton | Unbilled | 6.08
| 2026-06-15 | Fielding K Benton | Unbilled | 3.92
| 2026-06-15 | Fielding K Benton | Unbilled | 0.33
| 2026-06-15 | Seth Bibbs | Unbilled | 3.92
| 2026-06-15 | Seth Bibbs | Unbilled | 1.17
| 2026-06-16 | Alexander D Gazzola | Unbilled | 10
| 2026-06-16 | Alexander D Gazzola | Unbilled | 1
| 2026-06-16 | Fielding K Benton | Unbilled | 5.08
| 2026-06-16 | Fielding K Benton | Unbilled | 4.67
| 2026-06-16 | Seth Bibbs | Unbilled | 3.42
| 2026-06-16 | Seth Bibbs | Unbilled | 0.58
| 2026-06-16 | Seth Bibbs | Unbilled | 3.33
| 2026-06-17 | Fielding K Benton | Unbilled | 5.67
| 2026-06-17 | Fielding K Benton | Unbilled | 3.25
| 2026-06-18 | Fielding K Benton | Unbilled | 2.25
| 2026-06-18 | Fielding K Benton | Unbilled | 0.25
| 2026-06-18 | Fielding K Benton | Unbilled | 0.67
| 2026-06-22 | Fielding K Benton | Unbilled | 2.67
| 2026-06-22 | Fielding K Benton | Unbilled | 3.67
| 2026-06-23 | Fielding K Benton | Unbilled | 1.25
| 2026-06-24 | Alexander D Gazzola | Unbilled | 7.08
| 2026-06-24 | Alexander D Gazzola | Unbilled | 2.92
| 2026-06-24 | Alexander D Gazzola | Unbilled | 0.58
| 2026-06-24 | Fielding K Benton | Unbilled | 0.67
| 2026-06-24 | Fielding K Benton | Unbilled | 1.5
| 2026-06-26 | Alexander D Gazzola | Unbilled | 0.42
| 2026-06-26 | Alexander D Gazzola | Unbilled | 1.25
| 2026-06-26 | Fielding K Benton | Unbilled | 0.5
| 2026-06-30 | Fielding K Benton | Unbilled | 0.92
Total 06 Framing:Framing Labor |  |  |  | 974.53
06 Framing:Timber Framing Labour Cost
| 2026-05-29 | James McMann | Unbilled | 1.92
| 2026-05-29 | James McMann | Unbilled | 1.08
Total 06 Framing:Timber Framing Labour Cost |  |  |  | 3
14 Exterior Veneer:Siding Labor
| 2026-06-12 | Alexander D Gazzola | Unbilled | 5.08
| 2026-06-20 | Alexander D Gazzola | Unbilled | 7.08
| 2026-06-20 | Alexander D Gazzola | Unbilled | 2.92
| 2026-06-20 | Alexander D Gazzola | Unbilled | 1.42
Total 14 Exterior Veneer:Siding Labor |  |  |  | 16.5
21 Exterior Areas & Finishes:Landscaping
| 2026-04-02 | Alaa Kadah | Unbilled | 3.17
| 2026-04-15 | Alaa Kadah | Unbilled | 0
Total 21 Exterior Areas & Finishes:Landscaping |  |  |  | 3.17
22 Construction Clean Up:Clean Labour
| 2026-03-23 | Fielding K Benton | Unbilled | 0
| 2026-06-09 | Alaa Kadah | Unbilled | 4.5
| 2026-06-09 | Alaa Kadah | Unbilled | 2.75
| 2026-06-30 | Fielding K Benton | Unbilled | 1.33
Total 22 Construction Clean Up:Clean Labour |  |  |  | 8.58
24 Supervision:Project Managment
| 2026-02-25 | James McMann | Unbilled | 1.83
| 2026-05-27 | James McMann | Unbilled | 2.83
Total 24 Supervision:Project Managment |  |  |  | 4.66
1160.21
Total Timesheet |  |  |  | 1160.21

## Material
| Type | Date | Num | Memo | Amount
1047335 B.C. LTD (dba Complete Damp Proof
| Bill | 2026-03-05 | 11452 | Damproofing | 3379.95
Total 1047335 B.C. LTD (dba Complete Damp Proof |  |  |  |  | 3379.95
ABC Supply and Co
| Credit Card Charge | 2026-06-03 |  | Roofing Supply & Install | 2295.86
| Credit Card Credit | 2026-06-10 |  | Roofing Supply & Install | -492.1
| Credit Card Charge | 2026-06-30 | 257305 | Roofing Supply & Install | 871.84
| Bill | 2026-07-03 | 319570 | Roofing Supply & Install | 4113.69
| Credit Card Credit | 2026-07-03 |  | Roofing Supply & Install | -336.46
Total ABC Supply and Co |  |  |  |  | 6452.83
Andrew Sheret Ltd
| Bill | 2026-02-27 | 03-084405 | Backfill, Perimeter & Drain Material | 411.09
| Bill | 2026-03-02 | 03-084596 | Backfill, Perimeter & Drain Material | 1162.28
| Bill | 2026-03-07 | 03-085259 | Backfill, Perimeter & Drain Material | 408.36
| Bill | 2026-03-09 | 03-085292 | Backfill, Perimeter & Drain Material | 227.04
| Bill | 2026-03-10 | 03-085458 | Backfill, Perimeter & Drain Material | 627.47
| Credit | 2026-03-10 | 03-085563 | Backfill, Perimeter & Drain Material | -255.26
| Bill | 2026-03-12 | 03-085864 | Backfill, Perimeter & Drain Material | 533.88
| Bill | 2026-04-27 | 03-090686 | Backfill, Perimeter & Drain Material | 797.73
| Bill | 2026-05-12 | 03-092447 | Backfill, Perimeter & Drain Material | 510.81
| Bill | 2026-06-10 | 03-095733 | Backfill, Perimeter & Drain Material | 7.66
| Bill | 2026-06-12 | 03-095751 | Backfill, Perimeter & Drain Material | 159.4
| Bill | 2026-06-13 | 03-096046 | Backfill, Perimeter & Drain Material | 58.29
| Bill | 2026-06-17 | 03-096401 | Backfill, Perimeter & Drain Material | 8.16
| Bill | 2026-06-24 | 03-097184 | Backfill, Perimeter & Drain Material | 1800.54
| Bill | 2026-06-30 | 03-097706 | Backfill, Perimeter & Drain Material | 4431.97
| Bill | 2026-07-02 | 03-097946 | Backfill, Perimeter & Drain Material | 211.18
| Bill | 2026-07-06 | 03-098148 | Backfill, Perimeter & Drain Material | 1727.02
| Credit | 2026-07-07 | 03-096011 | Backfill, Perimeter & Drain Material | -6.07
Total Andrew Sheret Ltd |  |  |  |  | 12821.55
BC Housing Licensing & Consumer Services
| Bill | 2025-12-09 | 875433 | BC Housing Registration Fee | 40
Total BC Housing Licensing & Consumer Services |  |  |  |  | 40
BC Hydro
| Cheque | 2026-06-30 | Direct | BC Hydro | 4887.75
Total BC Hydro |  |  |  |  | 4887.75
Bryan's Mechanical Ltd.
| Bill | 2026-06-24 | 696-D396-1 | Mechanical Rough In & Finish | 29581.13
Total Bryan's Mechanical Ltd. |  |  |  |  | 29581.13
Chevron
| Credit Card Charge | 2026-06-11 |  | Framing Materials Cost | 36.89
| Credit Card Charge | 2026-06-17 |  | Framing Materials Cost | 47.34
| Credit Card Charge | 2026-06-23 |  | Framing Materials Cost | 250
| Credit Card Charge | 2026-07-13 |  | Framing Materials Cost | 250
Total Chevron |  |  |  |  | 584.23
City of Nanaimo
| Bill | 2026-01-13 | BP131412 | Building Permit Fees | 739.5
| Credit Card Charge | 2026-02-19 |  | Building Permit Fees | 7400.35
| Credit Card Charge | 2026-07-27 | BP131412 | Building Permit Fees | 76.5
Total City of Nanaimo |  |  |  |  | 8216.35
Coast To Coast Equipment Rentals LTD
| Bill | 2026-03-25 | R1692-1 | Specialty Tool & Equipment Rental | 1675.88
Total Coast To Coast Equipment Rentals LTD |  |  |  |  | 1675.88
Coastline Plumbing Ltd
| Bill | 2026-03-13 | 3142 | Plumbing Rough In & Finish | 1422.77
| Bill | 2026-06-30 | 3266 | Plumbing Rough In & Finish | 28004.55
Total Coastline Plumbing Ltd |  |  |  |  | 29427.32
DBL Disposal Services Ltd
| Bill | 2026-03-16 | 275197 | Portable Toilet | 78.75
| Bill | 2026-03-31 | 275170 | Portable Toilet | 130.4
| Bill | 2026-04-30 | 284099 | Portable Toilet | 183.75
| Bill | 2026-05-31 | 295928 | Portable Toilet | 183.75
| Bill | 2026-06-11 | 312822 | Disposal & Dump Fees | 1664.96
| Bill | 2026-06-30 | 307837 | Portable Toilet | 91.88
Total DBL Disposal Services Ltd |  |  |  |  | 2333.49
Ecolibrium Energy Solutions Inc.
| Bill | 2025-10-24 | 2354 | Energy Advisor | 918.75
Total Ecolibrium Energy Solutions Inc. |  |  |  |  | 918.75
Fielding K Benton.
| Cheque | 2026-02-20 | 372 | Backfill, Perimeter & Drain Material | 130.28
Total Fielding K Benton. |  |  |  |  | 130.28
Gregg Distributors (Nanaimo) Ltd.
| Credit Card Charge | 2026-06-17 |  | Framing Materials Cost | 132.38
Total Gregg Distributors (Nanaimo) Ltd. |  |  |  |  | 132.38
Harleen Parmar
| Cheque | 2026-05-27 | 429 | Roof Trusses | 20000
| Bill | 2026-05-31 |  | Roof Trusses | 23603.7
| Bill | 2026-05-31 |  | Floor System | 12383
Total Harleen Parmar |  |  |  |  | 55986.7
Heidelberg Materials Canada Limited
| Bill | 2026-02-20 | 3183511 | Foundation & Footings concrete | 9798.42
| Bill | 2026-03-03 | 3184417 | Foundation & Footings concrete | 13751.36
| Bill | 2026-03-13 | 3185376 | Concrete Skim Coat Materials | 5354.94
| Bill | 2026-06-19 | 3193797 | Garage Concrete Slab | 4074.01
Total Heidelberg Materials Canada Limited |  |  |  |  | 32978.73
Immersive Design Inc
| Bill | 2025-10-31 | 25103103 | Plan Desgin | 9246.3
Total Immersive Design Inc |  |  |  |  | 9246.3
Island Aggregates Ltd
| Credit Card Charge | 2026-03-02 |  | Backfill, Perimeter & Drain Material | 292.89
| Credit Card Charge | 2026-03-02 |  | Backfill, Perimeter & Drain Material | 256.66
| Credit Card Charge | 2026-03-03 |  | Backfill, Perimeter & Drain Material | 287.68
| Credit Card Charge | 2026-03-03 |  | Backfill, Perimeter & Drain Material | 284.2
| Credit Card Charge | 2026-03-06 |  | Backfill, Perimeter & Drain Material | 282.04
| Credit Card Charge | 2026-03-06 |  | Backfill, Perimeter & Drain Material | 288.55
| Credit Card Charge | 2026-03-06 |  | Backfill, Perimeter & Drain Material | 294.2
| Credit Card Charge | 2026-03-06 |  | Backfill, Perimeter & Drain Material | 574.93
| Credit Card Charge | 2026-03-09 |  | Backfill, Perimeter & Drain Material | 295.94
| Credit Card Charge | 2026-03-09 |  | Backfill, Perimeter & Drain Material | 296.37
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 290.28
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 296.37
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 282.04
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 283.34
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 286.38
| Credit Card Charge | 2026-03-10 |  | Backfill, Perimeter & Drain Material | 290.28
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 272.47
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 280.3
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 283.34
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 286.81
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 302.03
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 302.46
| Credit Card Charge | 2026-03-11 |  | Backfill, Perimeter & Drain Material | 305.93
| Credit Card Charge | 2026-03-12 |  | Backfill, Perimeter & Drain Material | 570.15
| Credit Card Charge | 2026-03-12 |  | Backfill, Perimeter & Drain Material | 560.58
| Credit Card Charge | 2026-03-12 |  | Backfill, Perimeter & Drain Material | 489.1
| Credit Card Charge | 2026-03-12 |  | Backfill, Perimeter & Drain Material | 476.22
| Credit Card Charge | 2026-03-13 |  | Backfill, Perimeter & Drain Material | 486.07
Total Island Aggregates Ltd |  |  |  |  | 9497.61
Island Concrete Pumping Ltd
| Bill | 2026-02-20 | 28128 | Concrete Pump Truck | 1167.77
| Bill | 2026-03-03 | 28163 | Concrete Pump Truck | 1317.12
| Bill | 2026-03-13 | 28193 | Concrete Pump Truck | 1179.53
Total Island Concrete Pumping Ltd |  |  |  |  | 3664.42
Island Electric Company
| Bill | 2026-06-24 | EWO-1278-1A | Electrical Rough In & Finish - Change Order | 7333.67
| Bill | 2026-06-24 | EWO-1278-1 | Electrical Rough In & Finish | 37834.41
| Bill | 2026-07-02 | 1278-2 | Electrical Rough In & Finish | 17394.3
Total Island Electric Company |  |  |  |  | 62562.38
J. Mayzes Excavating Ltd
| Bill | 2026-02-20 | 107036 | Excavation, Backfill, Perimeter & Drain Labour | 1743
| Bill | 2026-02-20 | 107038 | Excavation, Backfill, Perimeter & Drain Labour | 646.21
| Bill | 2026-03-13 | 107092 | Excavation, Backfill, Perimeter & Drain Labour | 459.38
| Bill | 2026-03-13 | 107093 | Excavation, Backfill, Perimeter & Drain Labour | 1378.13
| Bill | 2026-03-13 | 107094 | Excavation, Backfill, Perimeter & Drain Labour | 1378.13
| Bill | 2026-03-16 | 107101 | Excavation, Backfill, Perimeter & Drain Labour | 315
| Bill | 2026-03-16 | 107102 | Excavation, Backfill, Perimeter & Drain Labour | 921.38
| Bill | 2026-03-16 | 107100 | Excavation, Backfill, Perimeter & Drain Labour | 1023.75
| Bill | 2026-03-16 | 107099 | Excavation, Backfill, Perimeter & Drain Labour | 918.75
| Bill | 2026-03-16 | 107098 | Excavation, Backfill, Perimeter & Drain Labour | 876.75
| Bill | 2026-04-13 | 107150 | Excavation, Backfill, Perimeter & Drain Labour | 4432.58
| Bill | 2026-04-13 | 107147 | Excavation, Backfill, Perimeter & Drain Labour | 2210.25
| Bill | 2026-04-13 | 107149 | Excavation, Backfill, Perimeter & Drain Labour | 4320.75
| Bill | 2026-04-13 | 107146 | Excavation, Backfill, Perimeter & Drain Labour | 2793
| Bill | 2026-04-13 | 107148 | Excavation, Backfill, Perimeter & Drain Labour | 2449.13
| Bill | 2026-04-13 | 107145 | Excavation, Backfill, Perimeter & Drain Labour | 472.5
| Bill | 2026-04-17 | 107156 | Excavation, Backfill, Perimeter & Drain Labour | 763.17
| Bill | 2026-05-29 | 107255 | Excavation, Backfill, Perimeter & Drain Labour | 1372.88
| Bill | 2026-06-18 | 10728 | Excavation, Backfill, Perimeter & Drain Labour | 1286.25
| Bill | 2026-06-18 | 107289 | Excavation, Backfill, Perimeter & Drain Labour | 2520
| Bill | 2026-06-18 | 107290 | Excavation, Backfill, Perimeter & Drain Labour | 441
| Bill | 2026-07-02 | 107313 | Excavation, Backfill, Perimeter & Drain Labour | 1619.63
| Bill | 2026-07-02 | 107314 | Excavation, Backfill, Perimeter & Drain Labour | 3064.37
| Bill | 2026-07-02 | 107315 | Excavation, Backfill, Perimeter & Drain Labour | 700.88
| Bill | 2026-07-02 | 107316 | Excavation, Backfill, Perimeter & Drain Labour | 3671.35
| Bill | 2026-07-17 | 107339 | Excavation, Backfill, Perimeter & Drain Labour | 2638.13
| Bill | 2026-07-27 | 107370 | Excavation, Backfill, Perimeter & Drain Labour | 467.25
| Bill | 2026-07-27 | 107371 | Excavation, Backfill, Perimeter & Drain Labour | 1659
| Bill | 2026-07-27 | 107372 | Excavation, Backfill, Perimeter & Drain Labour | 2604.82
| Bill | 2026-07-27 | 107373 | Excavation, Backfill, Perimeter & Drain Labour | 2307.38
| Bill | 2026-07-27 | 107374 | Excavation, Backfill, Perimeter & Drain Labour | 1672.71
| Bill | 2026-07-27 | 107375 | Excavation, Backfill, Perimeter & Drain Labour | 1270.5
Total J. Mayzes Excavating Ltd |  |  |  |  | 54398.01
JE Anderson & Associates
| Bill | 2026-03-04 | 0067336 | Land Survey | 3447.82
| Bill | 2026-05-06 | 0067943 | Land Survey | 231.53
| Bill | 2026-06-08 | 0068298 | Land Survey | 807.98
| Bill | 2026-07-06 | 0068578 | Land Survey | 3484.54
| Bill | 2026-07-06 | 0068579 | Land Survey | 63.26
Total JE Anderson & Associates |  |  |  |  | 8035.13
JINGLEPOT GENERAL STORE
| Credit Card Charge | 2026-03-07 |  | Excavation, Backfill, Perimeter & Drain Labour | 42.76
| Credit Card Charge | 2026-03-20 | 326334 | Excavation, Backfill, Perimeter & Drain Labour | 79.05
| Credit Card Charge | 2026-03-26 | 328324 | Excavation, Backfill, Perimeter & Drain Labour | 83.16
| Credit Card Charge | 2026-04-05 |  | Excavation, Backfill, Perimeter & Drain Labour | 10.19
| Credit Card Charge | 2026-04-08 | 333601 | Excavation, Backfill, Perimeter & Drain Labour | 78.35
Total JINGLEPOT GENERAL STORE |  |  |  |  | 293.51
Joel
| Cheque | 2026-07-23 | Direct | Other - Alex & Joel & Kyle | 450
Total Joel |  |  |  |  | 450
JXN SOLUTIONS LTD
| Bill | 2026-03-16 | invoice 31 | Footings & Foundation Labor | 15750
Total JXN SOLUTIONS LTD |  |  |  |  | 15750
Kivela Contracting Ltd.
| Bill | 2026-01-16 | 2657 | Septic | 1890
| Bill | 2026-01-16 | 2657 | Septic | -94.5
Total Kivela Contracting Ltd. |  |  |  |  | 1795.5
Kyle Windle
| Bill | 2026-06-30 |  | Other - Alex & Joel & Kyle | 210
| Bill | 2026-07-17 |  | Other - Alex & Joel & Kyle | 175
Total Kyle Windle |  |  |  |  | 385
Lanson's Drywall Systems Ltd
| Bill | 2026-07-23 | 6253 | Drywall | 89461.6
Total Lanson's Drywall Systems Ltd |  |  |  |  | 89461.6
Lewkowich Engineering Associates Ltd
| Bill | 2026-03-10 | 103889 | Geotechnical Engineering | 289.17
| Bill | 2026-04-10 | 104329 | Geotechnical Engineering | 152.67
| Bill | 2026-05-11 | 104785 | Geotechnical Engineering | 305.34
| Bill | 2026-07-10 | 105769 | Geotechnical Engineering | 136.5
Total Lewkowich Engineering Associates Ltd |  |  |  |  | 883.68
Maxxam Insurance Services
| Bill | 2026-03-03 | 0071798 | Insurance | 4450
Total Maxxam Insurance Services |  |  |  |  | 4450
Metal Supermarkets
| Credit Card Charge | 2026-03-13 |  | Footings and Foundation Material | 12.61
Total Metal Supermarkets |  |  |  |  | 12.61
Mid Island Co-op
| Credit Card Charge | 2026-02-10 |  | Excavation, Backfill, Perimeter & Drain Labour | 960
| Credit Card Charge | 2026-03-02 |  | Excavation, Backfill, Perimeter & Drain Labour | 960
| Credit Card Charge | 2026-03-12 |  | Excavation, Backfill, Perimeter & Drain Labour | 960
| Credit Card Charge | 2026-04-01 |  | Excavation, Backfill, Perimeter & Drain Labour | 480
| Credit Card Charge | 2026-04-28 |  | Excavation, Backfill, Perimeter & Drain Labour | 480
| Credit Card Charge | 2026-06-03 |  | Framing Materials Cost | 480
| Credit Card Charge | 2026-06-25 |  | Framing Materials Cost | 480
Total Mid Island Co-op |  |  |  |  | 4800
Mission Island Group
| Bill | 2026-02-17 | MG56277 | Disposal & Dump Fees | 1168.65
| Bill | 2026-04-12 | MR469858 | Disposal & Dump Fees | 71.24
| Bill | 2026-06-09 | MR486354 | Disposal & Dump Fees | 55.76
| Bill | 2026-06-22 | MR489990 | Disposal & Dump Fees | 34.07
| Bill | 2026-06-25 | MR490687 | Disposal & Dump Fees | 24.78
| Bill | 2026-06-27 | MR491401 | Disposal & Dump Fees | 12.6
| Bill | 2026-06-30 | MR492192 | Disposal & Dump Fees | 56.96
| Bill | 2026-07-01 | MR492329 | Disposal & Dump Fees | 49.61
Total Mission Island Group |  |  |  |  | 1473.67
New-Line Hose & Fittings
| Bill | 2026-02-20 | IN2735196 | Footings and Foundation Material | 130.28
| Credit Card Charge | 2026-05-28 | IN2802284 | Framing Materials Cost | 99.86
| Credit Card Charge | 2026-06-17 |  | Framing Materials Cost | 22.33
Total New-Line Hose & Fittings |  |  |  |  | 252.47
Pacific Net & Twine
| Credit Card Charge | 2026-05-13 | 02344505 | Framing Materials Cost | 513.57
Total Pacific Net & Twine |  |  |  |  | 513.57
Petro Canada
| Credit Card Charge | 2026-05-10 | 133430 | Framing Materials Cost | 150
| Credit Card Charge | 2026-05-10 | 133427 | Framing Materials Cost | 150
| Credit Card Charge | 2026-05-10 | 133439 | Framing Materials Cost | 150
| Credit Card Charge | 2026-05-24 | 311599 | Framing Materials Cost | 200
| Credit Card Charge | 2026-06-12 |  | Framing Materials Cost | 75
| Credit Card Charge | 2026-06-12 |  | Framing Materials Cost | 4.8
| Credit Card Charge | 2026-06-19 | 180896 | Framing Materials Cost | 150
| Credit Card Charge | 2026-06-19 | 180890 | Framing Materials Cost | 150
| Credit Card Charge | 2026-06-26 | 146186 | Framing Materials Cost | 150
| Credit Card Charge | 2026-06-26 |  | Framing Materials Cost | 9.67
| Credit Card Charge | 2026-07-11 |  | Framing Materials Cost | 149.61
| Credit Card Charge | 2026-07-17 |  | Framing Materials Cost | 75
| Credit Card Charge | 2026-07-17 |  | Framing Materials Cost | 150
| Credit Card Charge | 2026-07-17 |  | Framing Materials Cost | 150
| Credit Card Charge | 2026-07-17 |  | Framing Materials Cost | 150
Total Petro Canada |  |  |  |  | 1864.08
Ply Gem Windows
| Bill | 2026-05-25 | 3238324 | Sliding Door | 15118.53
| Bill | 2026-05-25 | 3238325 | Windows | 25812.63
Total Ply Gem Windows |  |  |  |  | 40931.16
Print Three Nanaimo
| Bill | 2026-02-24 | 5-36457 | Plan Printing & Photocopying | 158.93
Total Print Three Nanaimo |  |  |  |  | 158.93
Rona 221227- Mcmann Group
| Bill | 2026-02-11 | 103-25181721 | Footings and Foundation Material | 96.75
| Bill | 2026-02-11 | 83323-10436131 | Footings and Foundation Material | 269.15
| Bill | 2026-02-16 | 83323-10437221 | Footings and Foundation Material | 332.64
| Bill | 2026-02-17 | 103-25183381 | Footings and Foundation Material | 11877.03
| Bill | 2026-02-18 | 104-27026191 | Footings and Foundation Material | 649.47
| Bill | 2026-02-23 | 103?25178881 | Footings and Foundation Material | 581.92
| Bill | 2026-02-23 | 103?25190601 | Footings and Foundation Material | 108.06
| Bill | 2026-03-02 | 103-25198351 | Footings and Foundation Material | 11546.35
| Credit | 2026-03-02 | 103-25198321CR | Footings and Foundation Material | -11820.14
| Bill | 2026-03-03 | 103-25198891 | Backfill, Perimeter & Drain Material | 2369.25
| Credit | 2026-03-03 | 103-25198921CR | Backfill, Perimeter & Drain Material | -2369.25
| Credit | 2026-03-03 | 104-27039671CR | Footings and Foundation Material | -649.47
| Bill | 2026-03-03 | 104-27039681 | Footings and Foundation Material | 183.64
| Bill | 2026-03-06 | 103-25198941 | Backfill, Perimeter & Drain Material | 2471.14
| Bill | 2026-03-08 | 83323-10444521 | Footings and Foundation Material | 96.37
| Bill | 2026-03-12 | 83323-10445991 | Footings and Foundation Material | 212.17
| Bill | 2026-03-16 | 103-25211741 | Framing Materials Cost | 356.54
| Bill | 2026-03-18 | 103-25214341 | Framing Materials Cost | 1133.28
| Credit | 2026-03-23 | 103-25217871CR | Framing Materials Cost | -77
| Bill | 2026-03-24 | 104-27064131 | Framing Materials Cost | 7854.28
| Bill | 2026-03-25 | 103-25220951 | Framing Materials Cost | 80.58
| Bill | 2026-03-30 | 103-25222411 | Framing Materials Cost | 14103.16
| Credit | 2026-03-31 | 103-25226061CR | Framing Materials Cost | -224.22
| Bill | 2026-03-31 | 103-25226171 | Framing Materials Cost | 224.22
| Bill | 2026-04-03 | 83323-10454461 | Framing Materials Cost | 297.91
| Bill | 2026-04-07 | 104-27080521 | Framing Materials Cost | 4177.56
| Bill | 2026-04-15 | 103-25239371 | Framing Materials Cost | 1637
| Credit Card Charge | 2026-04-18 | x8229100382 | Framing Materials Cost | 63.45
| Bill | 2026-04-20 | 103?25246351 | Framing Materials Cost | 224.89
| Bill | 2026-05-07 | 103-25265461 | Framing Materials Cost | 2178.89
| Bill | 2026-05-12 | 103-25272441 | Framing Materials Cost | 1876.9
| Bill | 2026-05-12 | 103-25272451 | Framing Materials Cost | 2565.09
| Bill | 2026-05-20 | 83323-10475251 | Framing Materials Cost | 34.7
| Bill | 2026-05-21 | 103-25281281 | Framing Materials Cost | 3192.65
| Bill | 2026-05-25 | 83323-10477381 | Framing Materials Cost | 192.47
| Bill | 2026-05-26 | 103-25285711 | Siding Materials | 403.74
| Bill | 2026-05-27 | 103-25288111 | Framing Materials Cost | 523.67
| Bill | 2026-05-27 | 83323-10478011 | Framing Materials Cost | 122.57
| Credit | 2026-05-29 | 103-25289941CR | Framing Materials Cost | -145.6
| Bill | 2026-05-29 | 103-25289981 | Framing Materials Cost | 145.6
| Bill | 2026-06-02 | 103-25293991 | Framing Materials Cost | 376.32
| Bill | 2026-06-03 | 83323-10481301 | Framing Materials Cost | 48.15
| Bill | 2026-06-04 | 103-25296581 | Framing Materials Cost | 166.37
| Bill | 2026-06-04 | 103-25296751 | Framing Materials Cost | 1072.63
| Bill | 2026-06-16 | 103-25308511 | Framing Materials Cost | 536.86
| Bill | 2026-06-16 | 103-25308571 | Framing Materials Cost | 151.15
| Bill | 2026-06-17 | 103-25296181 | Roofing Supply & Install | 16234.4
| Bill | 2026-07-13 | 103-25336661 | Framing Materials Cost | 23.19
| Bill | 2026-07-15 | 104-27207191 | Siding Materials | 9396.86
| Bill | 2026-07-16 | 104-27213641 | Siding Materials | 3760.85
| Credit | 2026-07-16 | 104-27215921CR | Siding Materials | -3760.85
| Bill | 2026-07-28 | 83323-10504501 | Patio/Drives/Walkways Concrete & Material | 16.12
Total Rona 221227- Mcmann Group |  |  |  |  | 84919.46
Sharecost Rentals & Sales
| Credit Card Charge | 2026-06-30 |  | Specialty Tool & Equipment Rental | 69.44
Total Sharecost Rentals & Sales |  |  |  |  | 69.44
SHERWIN-WILLIAMS
| Credit Card Charge | 2026-07-21 |  | Interior & Exterior Paint | 42.09
Total SHERWIN-WILLIAMS |  |  |  |  | 42.09
Slegg Building Materials
| Bill | 2026-02-13 | IN5453830 | Footings and Foundation Material | 229.69
| Bill | 2026-02-24 | IN5464800 | Footings and Foundation Material | 769.62
| Bill | 2026-02-25 | IN5465953 | Footings and Foundation Material | 646.83
| Bill | 2026-02-25 | IN5466475 | Footings and Foundation Material | 43.37
| Bill | 2026-02-26 | IN5467679 | Footings and Foundation Material | 75.41
| Bill | 2026-02-27 | IN5468448 | Footings and Foundation Material | 265.44
| Bill | 2026-03-02 | IN5471570 | Footings and Foundation Material | 27.94
| Bill | 2026-03-07 | IN5478756 | Backfill, Perimeter & Drain Material | 102.11
| Bill | 2026-03-13 | IN5486064 | Backfill, Perimeter & Drain Material | 48.5
| Bill | 2026-03-13 | IN5486236 | Footings and Foundation Material | 83.89
| Bill | 2026-03-17 | IN5490588 | Footings and Foundation Material | 62.53
| Bill | 2026-03-21 | IN5496082 | Footings and Foundation Material | 419.11
| Bill | 2026-03-23 | IN5497521 | Framing Materials Cost | 302.39
| Bill | 2026-03-26 | IN5501757 | Framing Materials Cost | 253.72
| Bill | 2026-03-30 | IN5506232 | Framing Materials Cost | 253.24
| Bill | 2026-03-30 | IN5507454 | Framing Materials Cost | 68.38
| Credit | 2026-03-31 | CR442850 | Framing Materials Cost | -17.14
| Bill | 2026-03-31 | IN5508162 | Framing Materials Cost | 30.04
| Bill | 2026-03-31 | IN5508881 | Framing Materials Cost | 147.43
| Bill | 2026-04-07 | IN5515738 | Framing Materials Cost | 514.91
| Bill | 2026-04-07 | IN5516315 | Framing Materials Cost | 372.72
| Bill | 2026-04-09 | IN5518906 | Framing Materials Cost | 110.7
| Bill | 2026-04-13 | IN5523868 | Framing Materials Cost | 646.51
| Bill | 2026-04-13 | IN5524358 | Framing Materials Cost | 84.89
| Bill | 2026-04-13 | IN5524361 | Framing Materials Cost | 111.49
| Bill | 2026-04-14 | IN5526061 | Framing Materials Cost | 185.12
| Bill | 2026-04-15 | IN5527570 | Framing Materials Cost | 104.23
| Bill | 2026-04-16 | IN5529480 | Framing Materials Cost | 277.41
| Bill | 2026-04-16 | IN5529982 | Framing Materials Cost | 13.31
| Bill | 2026-04-17 | IN5531157 | Framing Materials Cost | 175.79
| Bill | 2026-05-01 | IN5552211 | Framing Materials Cost | 604.19
| Bill | 2026-05-04 | IN5555954 | Framing Materials Cost | 183.01
| Bill | 2026-05-05 | IN5556574 | Framing Materials Cost | 171.08
| Bill | 2026-05-05 | IN5557196 | Framing Materials Cost | 22.34
| Bill | 2026-05-06 | IN5558987 | Framing Materials Cost | 36.53
| Bill | 2026-05-13 | IN5569181 | Framing Materials Cost | 42.55
| Bill | 2026-05-13 | IN5569754 | Framing Materials Cost | 459
| Credit Card Charge | 2026-05-26 | IN5585950 | Framing Materials Cost | 76.12
| Bill | 2026-05-27 | IN5588115 | Framing Materials Cost | 219.94
| Bill | 2026-05-27 | IN5589995 | Framing Materials Cost | 36.31
| Bill | 2026-05-29 | IN5591826 | Framing Materials Cost | 38.27
| Bill | 2026-06-01 | IN3-0000758 | Framing Materials Cost | 9.49
| Bill | 2026-06-01 | IN3-0000155 | Framing Materials Cost | 31.9
| Bill | 2026-06-01 | IN3-0003254 | Framing Materials Cost | 136.28
| Bill | 2026-06-03 | IN3-0008495 | Framing Materials Cost | 43.52
| Bill | 2026-06-03 | IN3-0007736 | Framing Materials Cost | 57.43
| Bill | 2026-06-03 | IN3-0007042 | Framing Materials Cost | 208.61
| Bill | 2026-06-04 | IN3-0009718 | Framing Materials Cost | 335.71
| Bill | 2026-06-04 | IN3-0009059 | Framing Materials Cost | 177.08
| Bill | 2026-06-06 | IN3-0013767 | Framing Materials Cost | 155.59
| Bill | 2026-06-08 | IN3-0019649 | Framing Materials Cost | 136.15
| Bill | 2026-06-08 | IN3-0016606 | Framing Materials Cost | 308.62
| Bill | 2026-06-09 | IN3-0019646 | Framing Materials Cost | 21.27
| Bill | 2026-06-10 | IN3-0020173 | Framing Materials Cost | 363.93
| Bill | 2026-06-11 | IN3-0024175 | Framing Materials Cost | 94.01
| Bill | 2026-06-11 | IN3-0022959 | Framing Materials Cost | 851.18
| Bill | 2026-06-16 | IN3-0032829 | Framing Materials Cost | 61.94
| Bill | 2026-06-16 | IN3-0031604 | Framing Materials Cost | 230.44
| Bill | 2026-06-18 | IN3-0037972 | Framing Materials Cost | 8.42
| Bill | 2026-06-18 | IN3-0037952 | Framing Materials Cost | 138.41
| Bill | 2026-06-20 | IN3-0041113 | Framing Materials Cost | 67.88
| Bill | 2026-06-22 | IN3-0042723 | Framing Materials Cost | 26.11
| Bill | 2026-06-24 | IN3-0047474 | Framing Materials Cost | 62.63
| Bill | 2026-06-30 | IN3-0059121 | Framing Materials Cost | 56.77
| Bill | 2026-07-02 | IN3-0061416 | Framing Materials Cost | 11.65
| Bill | 2026-07-02 | IN3-0060768 | Framing Materials Cost | 51.66
| Bill | 2026-07-02 | IN3-0062343 | Exterior Doors | 4246.39
| Bill | 2026-07-03 | IN3-0062352 | Exterior Doors | 552.55
| Bill | 2026-07-07 | IN3-0071112 | Exterior Doors | 1095.4
| Bill | 2026-07-08 | IN3-0072065 | Framing Materials Cost | 106.35
| Bill | 2026-07-08 | IN3-0073392 | Framing Materials Cost | 21.27
| Bill | 2026-07-09 | IN3-0074676 | Framing Materials Cost | 42.54
| Bill | 2026-07-11 | IN3-0078455 | Framing Materials Cost | 359.44
| Bill | 2026-07-11 | IN3-0078448 | Framing Materials Cost | 113.43
| Bill | 2026-07-13 | IN3-0080226 | Interior Doors | 265.98
| Bill | 2026-07-14 | IN3-0082628 | Framing Materials Cost | 14.1
| Bill | 2026-07-24 | IN3-0103949 | Framing Materials Cost | 204.66
Total Slegg Building Materials |  |  |  |  | 18967.71
Summit Tree Care Ltd.
| Bill | 2026-03-02 | 1713 | Excavation, Backfill, Perimeter & Drain Labour | 787.5
Total Summit Tree Care Ltd. |  |  |  |  | 787.5
Sunbelt Rentals
| Bill | 2026-02-27 | 79499564-0001 | Specialty Tool & Equipment Rental | 705.6
| Bill | 2026-06-18 | 79986406-0001 | Specialty Tool & Equipment Rental | 118.19
Total Sunbelt Rentals |  |  |  |  | 823.79
The Home Depot
| Credit Card Charge | 2026-04-05 | 70400241786 | Framing Materials Cost | 138.03
| Credit Card Charge | 2026-06-26 | 70400194340 | Framing Materials Cost | 260.45
| Credit Card Charge | 2026-07-01 | 288075 | Specialty Tool & Equipment Rental | 112.42
Total The Home Depot |  |  |  |  | 510.9
Travelers Canada
| Bill | 2025-12-09 | C1-0R0J3BB5 | Home Warranty Registration & Fees | 1250
Total Travelers Canada |  |  |  |  | 1250
Walkers Saw Shop
| Credit Card Charge | 2026-06-05 |  | Framing Materials Cost | 77.08
Total Walkers Saw Shop |  |  |  |  | 77.08
Westcoast Cutting and Coring Ltd.
| Bill | 2026-06-10 | 2115170 | Framing Materials Cost | 1804.69
Total Westcoast Cutting and Coring Ltd. |  |  |  |  | 1804.69
Westerra Equipment
| Bill | 2026-04-02 | SI142163 | Framing Materials Cost | 223.29
| Bill | 2026-04-02 | SI142162 | Framing Materials Cost | 20.81
Total Westerra Equipment |  |  |  |  | 244.1
Westshore Structural Engineering Ltd
| Bill | 2026-01-01 | 2025-1506 | Structural Engineering | 5775
| Bill | 2026-01-31 | 2026-0081 | Structural Engineering | 530.25
| Bill | 2026-02-28 | 2025-0188 | Structural Engineering | 908.67
| Bill | 2026-04-30 | 2026-0578 | Structural Engineering | 162.75
| Bill | 2026-06-30 | 2026-0908 | Structural Engineering | 472.5
Total Westshore Structural Engineering Ltd |  |  |  |  | 7849.17
Westwood Metals Ltd
| Bill | 2026-07-23 | 47824 | Siding Materials | 4371.36
Total Westwood Metals Ltd |  |  |  |  | 4371.36
Xtend Rentals Tool Sales
| Bill | 2026-03-09 | 138262-3 | Specialty Tool & Equipment Rental | 67.2
Total Xtend Rentals Tool Sales |  |  |  |  | 67.2
Total Vendor Detail |  |  |  |  | 622211.44