## Cost Breakdown
LINE ITEM | BUDGET | PREV. INVOICED | CURRENT INVOICE | TOTAL INVOICED | TO BE COMPLETED | OVER BUDGET | CHANGE ORDERS
DESIGN SERVICES
Plan Printing & Photocopying | 800 | 321.75 | 71.16 | 392.91 | 407.09 | 0 | 0
DESIGN SERVICES — Subtotal | 800 | 321.75 | 71.16 | 392.91 | 407.09 | 0 | 0
PERMITS & HOME WARRANTY
Building Permit Fees | 8500 | 14725.75 | 128.13 | 14853.88 | 0 | -6353.88 | 0
Home Warranty Registration & Fees | 11250 |  | 0 | 0 | 11250 | 0 | 0
BC Housing Registration Fee | 40 |  | 0 | 0 | 40 | 0 | 0
PERMITS & HOME WARRANTY — Subtotal | 19790 | 14725.75 | 128.13 | 14853.88 | 11290 | -6353.88 | 0
ENGINEERING FEES
Energy Advisor | 2000 | 975 |  | 975 | 1025 | 0 | 0
Land Survey | 6000 | 3971.15 | 892.5 | 4863.65 | 1136.35 | 0 | 0
Geotechnical Engineer | 4000 | 6537.4 | 352.4 | 6889.8 | 0 | -2889.8 | 0
Structural Engineering | 6000 |  | 0 | 0 | 6000 | 0 | 0
Change Order #2A Septic Drawing for BP |  | 1800 |  | 1800 | 0 | 0 | 1800
ENGINEERING FEES — Subtotal | 18000 | 13283.55 | 1244.9 | 14528.45 | 8161.35 | -2889.8 | 1800
SITE WORK
Excavation, Backfill, Perimeter & Drain Labour | 45000 | 7625 |  | 7625 | 37375 | 0 | 0
Concrete Coring and Cutting and Removal | 10000 |  |  | 0 | 10000 | 0 | 0
Contingency | 7000 |  |  | 0 | 7000 | 0 | 0
Change Order #2B Septic Field Work |  | 1732.55 |  | 1732.55 | 0 | 0 | 1732.55
SITE WORK — Subtotal | 62000 | 9357.55 | 0 | 9357.55 | 54375 | 0 | 1732.55
FOUNDATION
Footings & Foundation Material | 8422.72 |  | 8280.42 | 8280.42 | 142.3 | 0 | 0
Footings & Foundation Labour | 17635 |  | 17635 | 17635 | 0 | 0 | 0
Change Order #1 JXN Solutions: Footings and Foundation Labour |  | 0 | 11431.25 | 11431.25 | 0 | 0 | 11431.25
Footings & Foundation Concrete | 14800 |  | 13806.21 | 13806.21 | 993.79 | 0 | 0
Slab Prep - Labour | 1200 |  |  | 0 | 1200 | 0 | 0
Slab Prep - Material | 405.41 |  |  | 0 | 405.41 | 0 | 0
Garage Concrete Slab | 3600 |  |  | 0 | 3600 | 0 | 0
Concrete Slab - Skim Coat | 3200 |  |  | 0 | 3200 | 0 | 0
Concrete Slab Finishing Labour | 4887 |  |  | 0 | 4887 | 0 | 0
Concrete Pump Truck | 4500 |  | 3232.88 | 3232.88 | 1267.12 | 0 | 0
Damproofing | 7500 |  | 2735.6 | 2735.6 | 4764.4 | 0 | 0
Contingency | 5689.21 |  |  | 0 | 5689.21 | 0 | 0
FOUNDATION — Subtotal | 71839.34 | 0 | 57121.36 | 57121.36 | 26149.23 | 0 | 11431.25
FRAMING
Framing Materials | 44144.27 |  |  | 0 | 44144.27 | 0 | 0
Framing Labour | 45000 |  |  | 0 | 45000 | 0 | 0
Roof Trusses | 20915.15 |  |  | 0 | 20915.15 | 0 | 0
Engineering Parts | 4236.2 |  | 637.91 | 637.91 | 3598.29 | 0 | 0
Steel Beam in Garage | 1102.5 |  |  | 0 | 1102.5 | 0 | 0
Engineered Beams | 2692.58 |  |  | 0 | 2692.58 | 0 | 0
Contingency | 6657.07 |  |  | 0 | 6657.07 | 0 | 0
FRAMING — Subtotal | 124747.77 | 0 | 637.91 | 637.91 | 124109.86 | 0 | 0
WINDOWS
Windows | 29255.8 |  |  | 0 | 29255.8 | 0 | 0
Contingency | 2925.58 |  |  | 0 | 2925.58 | 0 | 0
WINDOWS — Subtotal | 32181.38 | 0 | 0 | 0 | 32181.38 | 0 | 0
DOORS
Exterior Doors and Interior Doors with Hardware | 8444.31 |  |  | 0 | 8444.31 | 0 | 0
Garage Doors | 13404.2 |  |  | 0 | 13404.2 | 0 | 0
Contingency | 2184.85 |  |  | 0 | 2184.85 | 0 | 0
DOORS — Subtotal | 24033.36 | 0 | 0 | 0 | 24033.36 | 0 | 0
ELECTRICAL
Electrical Rough In | 67865 |  |  | 0 | 67865 | 0 | 0
Electrical Fixtures | 6000 |  |  | 0 | 6000 | 0 | 0
Service Upgrade to 400amp | 26044 |  |  | 0 | 26044 | 0 | 0
Contingency | 9390.9 |  |  | 0 | 9390.9 | 0 | 0
Change Order #1 Island Electric - Electrical Underground Cable Repair |  | 1864.51 |  | 1864.51 | 0 | 0 | 1864.51
ELECTRICAL — Subtotal | 109299.9 | 1864.51 | 0 | 1864.51 | 109299.9 | 0 | 1864.51
PLUMBING
Plumbing Rough In | 25000 |  |  | 0 | 25000 | 0 | 0
Plumbing Fixtures | 20000 |  |  | 0 | 20000 | 0 | 0
Contingency | 4000 |  |  | 0 | 4000 | 0 | 0
PLUMBING — Subtotal | 49000 | 0 | 0 | 0 | 49000 | 0 | 0
HVAC
Mechanical Rough In | 31444 |  |  | 0 | 31444 | 0 | 0
Fireplace Unit Wood Burning | 7399 |  |  | 0 | 7399 | 0 | 0
BBQ Connection | 550 |  |  | 0 | 550 | 0 | 0
Gas/Propane Connection | 550 |  |  | 0 | 550 | 0 | 0
Contingency | 3994.3 |  |  | 0 | 3994.3 | 0 | 0
HVAC — Subtotal | 43937.3 | 0 | 0 | 0 | 43937.3 | 0 | 0
ROOFING
Roofing Supply & Install | 63000 |  |  | 0 | 63000 | 0 | 0
Metal Roof Painting | 30000 |  |  | 0 | 30000 | 0 | 0
Contingency | 5000 |  |  | 0 | 5000 | 0 | 0
ROOFING — Subtotal | 98000 | 0 | 0 | 0 | 98000 | 0 | 0
INSULATION & DRYWALL
Insulation | 32327.53 |  |  | 0 | 32327.53 | 0 | 0
Drywall | 37713.67 |  |  | 0 | 37713.67 | 0 | 0
Contingency | 7004 |  |  | 0 | 7004 | 0 | 0
INSULATION & DRYWALL — Subtotal | 77045.2 | 0 | 0 | 0 | 77045.2 | 0 | 0
EXTERIOR VENEER
Siding Labour | 20790 |  |  | 0 | 20790 | 0 | 0
Siding Materials | 35878.13 |  |  | 0 | 35878.13 | 0 | 0
Soffit Supply & Install | 5800 |  |  | 0 | 5800 | 0 | 0
Gutters Supply & Install | 3948 |  |  | 0 | 3948 | 0 | 0
Trim Labour | 5370 |  |  | 0 | 5370 | 0 | 0
Contingency | 5381.71 |  |  | 0 | 5381.71 | 0 | 0
EXTERIOR VENEER — Subtotal | 77167.84 | 0 | 0 | 0 | 77167.84 | 0 | 0
MASONRY
Interior Masonry - Supply & Install | 10400 |  |  | 0 | 10400 | 0 | 0
Contingency | 1040 |  |  | 0 | 1040 | 0 | 0
MASONRY — Subtotal | 11440 | 0 | 0 | 0 | 11440 | 0 | 0
CABINETRY & COUNTERTOPS
Cabinetry Supply and Install | 36980 |  |  | 0 | 36980 | 0 | 0
Countertop Supply & Install | 10380 |  |  | 0 | 10380 | 0 | 0
Walk In Closet | 6020 |  |  | 0 | 6020 | 0 | 0
Contingency | 5338 |  |  | 0 | 5338 | 0 | 0
CABINETRY & COUNTERTOPS — Subtotal | 58718 | 0 | 0 | 0 | 58718 | 0 | 0
INTERIOR FINISHING
Finishing Carpentry | 18000 |  |  | 0 | 18000 | 0 | 0
Interior Trim Materials | 13413.68 |  |  | 0 | 13413.68 | 0 | 0
Stair System Materials | 2400 |  |  | 0 | 2400 | 0 | 0
Bathroom Hardware | 500 |  |  | 0 | 500 | 0 | 0
Shower Glass Doors | 6500 |  |  | 0 | 6500 | 0 | 0
Mirrors | 1000 |  |  | 0 | 1000 | 0 | 0
Mantle | 1200 |  |  | 0 | 1200 | 0 | 0
Interior Cedar Beam Wraps/False Beams | 4919.37 |  |  | 0 | 4919.37 | 0 | 0
Shiplap for Electric Fireplace | 1067.6 |  |  | 0 | 1067.6 | 0 | 0
Contingency | 3109.95 |  |  | 0 | 3109.95 | 0 | 0
INTERIOR FINISHING — Subtotal | 52110.6 | 0 | 0 | 0 | 52110.6 | 0 | 0
WOOD FLOOR COVERINGS
Flooring Material - Addition | 7600 |  |  | 0 | 7600 | 0 | 0
Flooring Install Labour - Addition | 5700 |  |  | 0 | 5700 | 0 | 0
Floor Sanding & Prep | 6000 |  |  | 0 | 6000 | 0 | 0
Protective Floor Covering | 500 |  |  | 0 | 500 | 0 | 0
Old Flooring Removal - Existing House | 4800 |  |  | 0 | 4800 | 0 | 0
Flooring Material - Existing House | 9450 |  |  | 0 | 9450 | 0 | 0
Flooring Installation - Existing House | 6750 |  |  | 0 | 6750 | 0 | 0
Contingency | 1980 |  |  | 0 | 1980 | 0 | 0
WOOD FLOOR COVERINGS — Subtotal | 42780 | 0 | 0 | 0 | 42780 | 0 | 0
TILE
Floor Tile Material - Addition | 2532 |  |  | 0 | 2532 | 0 | 0
Floor Tile Install Labour - Addition | 2534 |  |  | 0 | 2534 | 0 | 0
Floor Tile Prep | 1000 |  |  | 0 | 1000 | 0 | 0
Wall Tile Material (Ensuite & Main Bath Shower) | 2726.7 |  |  | 0 | 2726.7 | 0 | 0
Wall Tile Labour (Ensuite & Main Bath Shower) | 4070 |  |  | 0 | 4070 | 0 | 0
Backsplash Tile Material | 400 |  |  | 0 | 400 | 0 | 0
Backsplash Tile Labour | 1200 |  |  | 0 | 1200 | 0 | 0
Heated Floor Prep | 2495.5 |  |  | 0 | 2495.5 | 0 | 0
Thermostats | 610.42 |  |  | 0 | 610.42 | 0 | 0
Ensuite Shower Linear Drain | 1000 |  |  | 0 | 1000 | 0 | 0
Floor Tile Material - Existing House | 3000 |  |  | 0 | 3000 | 0 | 0
Floor Tile Installation - Existing House | 5000 |  |  | 0 | 5000 | 0 | 0
Floor Tile Removal - Existing House | 1200 |  |  | 0 | 1200 | 0 | 0
Contingency | 1806.86 |  |  | 0 | 1806.86 | 0 | 0
TILE — Subtotal | 29575.48 | 0 | 0 | 0 | 29575.48 | 0 | 0
PAINT
Interior Paint | 22000 |  |  | 0 | 22000 | 0 | 0
Exterior Paint | 8500 |  |  | 0 | 8500 | 0 | 0
Door Painting & Staining | 2500 |  |  | 0 | 2500 | 0 | 0
Interior Staining T&G and Beams | 8000 |  |  | 0 | 8000 | 0 | 0
Contingency | 4100 |  |  | 0 | 4100 | 0 | 0
PAINT — Subtotal | 45100 | 0 | 0 | 0 | 45100 | 0 | 0
EXTERIOR HARDSCAPE
Patio Driveway Stone Removal | 5000 |  |  | 0 | 5000 | 0 | 0
New Concrete Driveway to New Garage Bays Material | 8600 |  |  | 0 | 8600 | 0 | 0
New Concrete Driveway Finishing | 4825 |  |  | 0 | 4825 | 0 | 0
Forming Driveway Labour | 3000 |  |  | 0 | 3000 | 0 | 0
EXTERIOR HARDSCAPE — Subtotal | 21425 | 0 | 0 | 0 | 21425 | 0 | 0
CONSTRUCTION CLEAN UP
Clean Up Labour | 10000 |  |  | 0 | 10000 | 0 | 0
Disposal & Dump Fees | 5500 |  |  | 0 | 5500 | 0 | 0
Dumpster Rental | 1500 |  |  | 0 | 1500 | 0 | 0
Final Site Clean | 2500 |  |  | 0 | 2500 | 0 | 0
CONSTRUCTION CLEAN UP — Subtotal | 19500 | 0 | 0 | 0 | 19500 | 0 | 0
JOBSITE FACILITIES
Portable Washroom | 1200 |  | 97.58 | 97.58 | 1102.42 | 0 | 0
Site Signage | 1500 |  |  | 0 | 1500 | 0 | 0
Tool & Rental Equipment | 1000 |  |  | 0 | 1000 | 0 | 0
Scaffolding | 3500 |  |  | 0 | 3500 | 0 | 0
JOBSITE FACILITIES — Subtotal | 7200 | 0 | 97.58 | 97.58 | 7102.42 | 0 | 0
PROJECT MANAGEMENT
Management & Supervision | 25200 | 10186.2 | 1549.8 | 11736 | 13464 | 0 | 0
Credit - Management Billing as per Pricing Contract |  | -5000 |  | -5000 | 5000 | 0 | 0
Accounting & Admin | 12600 | 720 | 900 | 1620 | 10980 | 0 | 0
PROJECT MANAGEMENT — Subtotal | 37800 | 5906.2 | 2449.8 | 8356 | 29444 | 0 | 0
MISCELLANEOUS
Travel | 8628.48 | 435.6 | 737.1 | 1172.7 | 7455.78 | 0 | 0
Deficiencies | 5000 |  | 0 | 0 | 5000 | 0 | 0
Demolition | 23400 |  |  | 0 | 23400 | 0 | 0
Demolition Dembri removal labour | 2000 |  |  | 0 | 2000 | 0 | 0
MISCELLANEOUS — Subtotal | 39028.48 | 435.6 | 737.1 | 1172.7 | 37855.78 | 0 | 0
Project Subtotal | 1172519.65 | 45894.91 | 62487.94 | 108382.85 | 1090208.79 | -9243.68 | 16828.31
15% Mark-up | 175877.9475 | 4979.8845 | 8895.156 | 13875.0405 | 163531.3185 | -433.47 | 2524.2465
GST (5%) | 67419.8799 | 2543.7397 | 3569.1548 | 6112.8945 | 62687.0054 | -483.8575 | 967.6278
PROJECT TOTAL | 1415817.4774 | 53418.5342 | 74952.2508 | 128370.785 | 1316427.1139 | -10161.0075 | 20320.1843
COLOUR LEGEND

## Timesheet
LINE ITEM | Date | Name | Billing Status | Duration | Rate | Amount
Project Managment
| 2025-05-06 | Russell McMann | Unbilled | 3 | 90 | 270
| 2025-05-14 | James McMann | Unbilled | 1.5 | 90 | 135
| 2025-05-21 | James McMann | Unbilled | 1.5 | 90 | 135
| 2025-05-30 | James McMann | Unbilled | 4 | 90 | 360
| 2025-06-02 | James McMann | Unbilled | 1.68 | 90 | 151.2
| 2025-06-03 | James McMann | Unbilled | 5.17 | 90 | 465.3
| 2025-06-04 | Abdullah Ibn Alamir | Unbilled | 4 | 90 | 360
| 2025-06-04 | James McMann | Unbilled | 3.33 | 90 | 299.7
| 2025-06-04 | James McMann | Unbilled | 1.67 | 90 | 150.3
| 2025-06-05 | Abdullah Ibn Alamir | Unbilled | 5 | 90 | 450
| 2025-06-05 | James McMann | Unbilled | 2.17 | 90 | 195.3
| 2025-06-16 | Russell McMann | Unbilled | 3 | 90 | 270
| 2025-06-18 | James McMann | Unbilled | 4.5 | 90 | 405
| 2025-06-22 | Abdullah Ibn Alamir | Unbilled | 5.67 | 90 | 510.3
| 2025-06-27 | Abdullah Ibn Alamir | Unbilled | 4.83 | 90 | 434.7
| 2025-06-27 | Kevin Mammen | Unbilled | 3.67 | 90 | 330.3
| 2025-09-25 | James McMann | Unbilled | 3 | 90 | 270
| 2025-10-02 | James McMann | Unbilled | 5.67 | 90 | 510.3
| 2025-10-08 | Russell McMann | Unbilled | 2 | 90 | 180
| 2025-10-09 | Kevin Mammen | Unbilled | 2.67 | 90 | 240.3
| 2025-10-15 | James McMann | Unbilled | 2.33 | 90 | 209.7
| 2025-10-15 | Kevin Mammen | Unbilled | 5.83 | 90 | 524.7
| 2025-10-17 | Kevin Mammen | Unbilled | 1.83 | 90 | 164.7
| 2025-10-22 | James McMann | Unbilled | 2.33 | 90 | 209.7
| 2025-11-13 | James McMann | Unbilled | 2.17 | 90 | 195.3
| 2025-11-18 | Kevin Mammen | Unbilled | 0.33 | 90 | 29.7
| 2025-12-03 | Kevin Mammen | Unbilled | 6.33 | 90 | 569.7
| 2025-12-09 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2025-12-12 | Abdullah Ibn Alamir | Unbilled | 4.5 | 90 | 405
| 2025-12-16 | Kevin Mammen | Unbilled | 3.67 | 90 | 330.3
| 2026-01-21 | Abdullah Ibn Alamir | Unbilled | 0.67 | 90 | 60.3
| 2026-04-17 | James McMann | Unbilled | 3 | 90 | 270
| 2026-04-20 | Russell McMann | Unbilled | 2 | 90 | 180
| 2026-04-20 | James McMann | Unbilled | 2 | 90 | 180
| 2026-04-22 | James McMann | Unbilled | 1.5 | 90 | 135
| 2026-04-28 | James McMann | Unbilled | 2.08 | 90 | 187.2
| 2026-04-29 | James McMann | Unbilled | 2.25 | 90 | 202.5
| 2026-04-30 | James McMann | Unbilled | 1.16 | 90 | 104.4
| 2026-05-04 | James McMann | Unbilled | 1 | 90 | 90
| 2026-05-06 | James McMann | Unbilled | 0.67 | 90 | 60.3
| 2026-05-06 | James McMann | Unbilled | 0.41 | 90 | 36.9
| 2026-05-11 | James McMann | Unbilled | 1.58 | 90 | 142.2
| 2026-05-14 | James McMann | Unbilled | 1.83 | 90 | 164.7
| 2026-05-14 | James McMann | Unbilled | 0.58 | 90 | 52.2
| 2026-05-19 | James McMann | Unbilled | 3.58 | 90 | 322.2
| 2026-05-21 | James McMann | Unbilled | 0.25 | 90 | 22.5
| 2026-05-21 | James McMann | Unbilled | 0.33 | 90 | 29.7
| 2026-05-25 | James McMann | Unbilled | 1.08 | 90 | 97.2
| 2026-05-28 | Russell McMann | Unbilled | 3 | 90 | 270
| 2026-05-28 | James McMann | Unbilled | 2.91 | 90 | 261.9
Total Project Managment |  |  |  | 130.4 |  | 11736
Travel Time
| 2026-04-17 | James McMann | Unbilled | 1.33 | 90 | 119.7
| 2026-04-20 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-04-22 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-04-30 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-06 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-11 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-14 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-19 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-21 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-25 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-28 | James McMann | Unbilled | 1.17 | 90 | 105.3
Total Travel Time |  |  |  | 13.03 |  | 1172.7
Total Timesheet |  |  |  | 143.43 |  | 12908.7

## Material
LINE ITEM | Type | Date | Num | Memo | Amount
1047335 B.C. LTD (dba Complete Damp Proof
| Bill | 2026-05-27 | 11561 | 1047335 B.C. LTD (dba Complete Damp Proof Damp proofing 11561 | 2735.6
Total 1047335 B.C. LTD (dba Complete Damp Proof |  |  |  |  | 2735.6
DBL Disposal Services Ltd
| Bill | 2026-05-29 | 305329 | DBL Portable Washroom- 305329 | 75
| Bill | 2026-05-31 | 305327 | DBL Disposal Services Ltd Portable Washroom- 305327 | 22.58
Total DBL Disposal Services Ltd |  |  |  |  | 97.58
Ecolibrium Energy Solutions Inc.
| Bill | 2025-10-19 | 2344 | Ecolibrium Energy Solutions Inc. Energy Advisor Report 2344 | 975
Total Ecolibrium Energy Solutions Inc. |  |  |  |  | 975
Heidelberg Materials Canada Limited
| Bill | 2026-05-12 | 3190336 | Heidelberg Materials Canada Limited Concrete Footings 3190336 | 6107.56
| Bill | 2026-05-21 | 3191123 | Heidelberg Materials Canada Limited Concrete Walls 3191123 | 7698.65
Total Heidelberg Materials Canada Limited |  |  |  |  | 13806.21
Island Concrete Pumping Ltd
| Bill | 2026-05-12 | 28435 | Island Concrete Pumping Ltd Concrete Pump Truck 28435 | 1482.88
| Bill | 2026-05-21 | 28478 | Island Concrete Pumping Ltd Concrete Pump Truck 28478 | 1750
Total Island Concrete Pumping Ltd |  |  |  |  | 3232.88
Island Electric Company
| Bill | 2026-04-30 | EWO-1189-1A | Island Electric Company Change Order Underground Cable Replacement 1189-1 | 1864.51
Total Island Electric Company |  |  |  |  | 1864.51
JE Anderson & Associates
| Bill | 2025-11-13 | 0066328 | JE Anderson & Associates Survey 0066328 | 3760.4
| Bill | 2026-02-10 | 0067130 | JE Anderson & Associates Survey 0067130 | 210.75
| Bill | 2026-05-06 | 0067962 | JE Anderson & Associates Survey 0067962 | 892.5
Total JE Anderson & Associates |  |  |  |  | 4863.65
JXN SOLUTIONS LTD
| Bill | 2026-05-28 | invoice 39 | JXN SOLUTIONS LTD Footings and Foundation Labour invoice 39 | 17635
| Bill | 2026-05-28 | invoice 39 | JXN SOLUTIONS LTD Change Order Footings and Foundation Labour invoice 39 | 11431.25
Total JXN SOLUTIONS LTD |  |  |  |  | 29066.25
Kivela Contracting Ltd.
| Bill | 2026-01-16 | 2658 | Kivela Contracting Ltd. Septic Design and Permit 2658 | 1800
| Bill | 2026-04-30 | 2694 | Kivela Contracting Ltd. Site Work 2694 | 7625
| Bill | 2026-04-30 | 2694 | Kivela Contracting Ltd. Change Order Septic Field Work 2694 | 1732.55
Total Kivela Contracting Ltd. |  |  |  |  | 11157.55
Lewkowich Engineering Associates Ltd
| Bill | 2025-12-10 | 102800 | Lewkowich Engineering Associates Ltd Geotechnical Assessment Report 102800 | 3760
| Bill | 2026-02-09 | 103557 | Lewkowich Engineering Associates Ltd Geotechnical Assessment Report 103557 | 300
| Bill | 2026-04-10 | 104422 | Lewkowich Engineering Associates Ltd Geotechnical Engineering 104422 | 2477.4
| Bill | 2026-05-11 | 104886 | Lewkowich Engineering Associates Ltd Geotechnical Engineering 104886 | 352.4
Total Lewkowich Engineering Associates Ltd |  |  |  |  | 6889.8
Print Three Nanaimo
| Bill | 2026-04-16 | 5-36986 | Print Three Nanaimo Revised Plan Printing 5-36986 | 321.75
| Bill | 2026-05-05 | 5-37167 | Print Three Nanaimo Plan Printing 5-37167 | 71.16
Total Print Three Nanaimo |  |  |  |  | 392.91
Regional District of Nanaimo
| Bill | 2025-12-16 | 2182719713 | Regional District of Nanaimo Building Permit Fees 2182719713 | 1025
| Bill | 2026-03-24 | PR20250000587 | Regional District of Nanaimo Building Permit PR20250000587 | 13700.75
| Credit Card Charge | 2026-05-07 | 2405438517 | Regional District of Nanaimo BP Revision 2405438517 | 128.13
Total Regional District of Nanaimo |  |  |  |  | 14853.88
Rona 221227- Mcmann Group
| Bill | 2026-05-05 | 103-25261351 | Rona Footings and Foundation Material 103-25261351 | 7268.71
| Bill | 2026-05-06 | 103-25259301 | Rona Engineering Material 103-25259301 | 637.91
Total Rona 221227- Mcmann Group |  |  |  |  | 7906.62
Slegg Building Materials
| Bill | 2026-05-11 | IN5565137 | Slegg Building Material Footings and Foundation Material IN5565137 | 215.54
| Bill | 2026-05-12 | IN5567055 | Slegg Building Material Footings and Foundation Material IN5567055 | 335.43
| Bill | 2026-05-14 | IN5570960 | Slegg Building Material Footings and Foundation Material IN5570960 | 207.15
| Bill | 2026-05-14 | IN5571123 | Slegg Building Material Footings and Foundation Material IN5571123 | 253.59
Total Slegg Building Materials |  |  |  |  | 1011.71
Total Vendor Detail |  |  |  |  | 98854.15