## Cost Breakdown
LINE ITEM | BUDGET | PREV. INVOICED | CURRENT INVOICE | TOTAL INVOICED | TO BE COMPLETED | OVER BUDGET | CHANGE ORDERS
DESIGN SERVICES
Plan Printing & Photocopying | 800 | 392.91 | 0 | 392.91 | 407.09 | 0 | 0
DESIGN SERVICES — Subtotal | 800 | 392.91 | 0 | 392.91 | 407.09 | 0 | 0
PERMITS & HOME WARRANTY
Building Permit Fees | 8500 | 14853.88 | 0 | 14853.88 | 0 | -6353.88 | 0
Home Warranty Registration & Fees | 11250 |  | 0 | 0 | 11250 | 0 | 0
BC Housing Registration Fee | 40 |  | 0 | 0 | 40 | 0 | 0
PERMITS & HOME WARRANTY — Subtotal | 19790 | 14853.88 | 0 | 14853.88 | 11290 | -6353.88 | 0
ENGINEERING FEES
Energy Advisor | 2000 | 975 |  | 975 | 1025 | 0 | 0
Land Survey | 6000 | 4863.65 | 817 | 5680.65 | 319.35 | 0 | 0
Geotechnical Engineer | 4000 | 6889.8 | 130 | 7019.8 | 0 | -3019.8 | 0
Structural Engineering | 6000 |  | 0 | 0 | 6000 | 0 | 0
Change Order #2A Septic Drawing for BP |  | 1800 |  | 1800 | 0 | 0 | 1800
ENGINEERING FEES — Subtotal | 18000 | 14528.45 | 947 | 15475.45 | 7344.35 | -3019.8 | 1800
SITE WORK
Excavation, Backfill, Perimeter & Drain Labour | 43275 | 7625 | 25175.55 | 32800.55 | 10474.45 | 0 | 0
Site Work - Outside Scope of Work | 1725 |  | 1725 | 1725 | 0 | 0 | 0
Concrete Coring and Cutting and Removal | 10000 |  | 900 | 900 | 9100 | 0 | 0
Contingency | 7000 |  |  | 0 | 7000 | 0 | 0
Change Order #2B Septic Field Work |  | 1732.55 |  | 1732.55 | 0 | 0 | 1732.55
SITE WORK — Subtotal | 62000 | 9357.55 | 27800.55 | 37158.1 | 26574.45 | 0 | 1732.55
FOUNDATION
Footings & Foundation Material | 8422.72 | 8280.42 | 130.38 | 8410.8 | 11.92 | 0 | 0
Footings & Foundation Labour | 17635 | 17635 |  | 17635 | 0 | 0 | 0
Change Order #1 JXN Solutions: Footings and Foundation Labour |  | 11431.25 |  | 11431.25 | 0 | 0 | 11431.25
Footings & Foundation Concrete | 14800 | 13806.21 |  | 13806.21 | 993.79 | 0 | 0
Slab Prep - Labour | 1200 |  | 806.3 | 806.3 | 393.7 | 0 | 0
Slab Prep - Material | 405.41 |  |  | 0 | 405.41 | 0 | 0
Garage Concrete Slab | 3600 |  |  | 0 | 3600 | 0 | 0
Concrete Slab - Skim Coat | 3200 |  | 2243.79 | 2243.79 | 956.21 | 0 | 0
Concrete Slab Finishing Labour | 4887 |  | 1440 | 1440 | 3447 | 0 | 0
Concrete Pump Truck | 4500 | 3232.88 |  | 3232.88 | 1267.12 | 0 | 0
Damproofing | 7500 | 2735.6 |  | 2735.6 | 4764.4 | 0 | 0
Contingency | 5689.21 |  |  | 0 | 5689.21 | 0 | 0
FOUNDATION — Subtotal | 71839.34 | 57121.36 | 4620.47 | 61741.83 | 21528.76 | 0 | 11431.25
FRAMING
Framing Materials | 44144.27 |  | 22477.74 | 22477.74 | 21666.53 | 0 | 0
Framing Labour | 45000 |  |  | 0 | 45000 | 0 | 0
Roof Trusses | 20915.15 |  |  | 0 | 20915.15 | 0 | 0
Engineering Parts | 4236.2 | 637.91 |  | 637.91 | 3598.29 | 0 | 0
Steel Beam in Garage | 1102.5 |  |  | 0 | 1102.5 | 0 | 0
Engineered Beams | 2692.58 |  | 983.06 | 983.06 | 1709.52 | 0 | 0
Contingency | 6657.07 |  |  | 0 | 6657.07 | 0 | 0
FRAMING — Subtotal | 124747.77 | 637.91 | 23460.8 | 24098.71 | 100649.06 | 0 | 0
WINDOWS
Windows | 29255.8 |  |  | 0 | 29255.8 | 0 | 0
Contingency | 2925.58 |  |  | 0 | 2925.58 | 0 | 0
WINDOWS — Subtotal | 32181.38 | 0 | 0 | 0 | 32181.38 | 0 | 0
DOORS
Exterior Doors and Interior Doors with Hardware | 8444.31 |  |  | 0 | 8444.31 | 0 | 0
Garage Doors | 13404.2 |  |  | 0 | 13404.2 | 0 | 0
Contingency | 2184.85 |  |  | 0 | 2184.85 | 0 | 0
DOORS — Subtotal | 24033.36 | 0 | 0 | 0 | 24033.36 | 0 | 0
ELECTRICAL
Electrical Rough In | 67865 |  |  | 0 | 67865 | 0 | 0
Electrical Fixtures | 6000 |  |  | 0 | 6000 | 0 | 0
Service Upgrade to 400amp | 26044 |  | 13022 | 13022 | 13022 | 0 | 0
Contingency | 9390.9 |  |  | 0 | 9390.9 | 0 | 0
Change Order #1 Island Electric - Electrical Underground Cable Repair |  | 1864.51 |  | 1864.51 | 0 | 0 | 1864.51
Change Order 3: Electrical Change Order - 400A Service Upgrade & Underground Extra Work |  |  | 6098.78 | 6098.78 | 0 | 0 | 6098.78
ELECTRICAL — Subtotal | 109299.9 | 1864.51 | 19120.78 | 20985.29 | 96277.9 | 0 | 7963.29
PLUMBING
Plumbing Rough In | 25000 |  | 2520.41 | 2520.41 | 22479.59 | 0 | 0
Plumbing Fixtures | 20000 |  |  | 0 | 20000 | 0 | 0
Contingency | 4000 |  |  | 0 | 4000 | 0 | 0
PLUMBING — Subtotal | 49000 | 0 | 2520.41 | 2520.41 | 46479.59 | 0 | 0
HVAC
Mechanical Rough In | 31444 |  |  | 0 | 31444 | 0 | 0
Fireplace Unit Wood Burning | 7399 |  |  | 0 | 7399 | 0 | 0
BBQ Connection | 550 |  |  | 0 | 550 | 0 | 0
Gas/Propane Connection | 550 |  |  | 0 | 550 | 0 | 0
Contingency | 3994.3 |  |  | 0 | 3994.3 | 0 | 0
HVAC — Subtotal | 43937.3 | 0 | 0 | 0 | 43937.3 | 0 | 0
ROOFING
Roofing Supply & Install | 63000 |  |  | 0 | 63000 | 0 | 0
Metal Roof Painting | 30000 |  |  | 0 | 30000 | 0 | 0
Contingency | 5000 |  |  | 0 | 5000 | 0 | 0
ROOFING — Subtotal | 98000 | 0 | 0 | 0 | 98000 | 0 | 0
INSULATION & DRYWALL
Insulation | 32327.53 |  |  | 0 | 32327.53 | 0 | 0
Drywall | 37713.67 |  |  | 0 | 37713.67 | 0 | 0
Contingency | 7004 |  |  | 0 | 7004 | 0 | 0
INSULATION & DRYWALL — Subtotal | 77045.2 | 0 | 0 | 0 | 77045.2 | 0 | 0
EXTERIOR VENEER
Siding Labour | 20790 |  |  | 0 | 20790 | 0 | 0
Siding Materials | 35878.13 |  |  | 0 | 35878.13 | 0 | 0
Soffit Supply & Install | 5800 |  |  | 0 | 5800 | 0 | 0
Gutters Supply & Install | 3948 |  |  | 0 | 3948 | 0 | 0
Trim Labour | 5370 |  |  | 0 | 5370 | 0 | 0
Contingency | 5381.71 |  |  | 0 | 5381.71 | 0 | 0
EXTERIOR VENEER — Subtotal | 77167.84 | 0 | 0 | 0 | 77167.84 | 0 | 0
MASONRY
Interior Masonry - Supply & Install | 10400 |  |  | 0 | 10400 | 0 | 0
Contingency | 1040 |  |  | 0 | 1040 | 0 | 0
MASONRY — Subtotal | 11440 | 0 | 0 | 0 | 11440 | 0 | 0
CABINETRY & COUNTERTOPS
Cabinetry Supply and Install | 36980 |  |  | 0 | 36980 | 0 | 0
Countertop Supply & Install | 10380 |  |  | 0 | 10380 | 0 | 0
Walk In Closet | 6020 |  |  | 0 | 6020 | 0 | 0
Contingency | 5338 |  |  | 0 | 5338 | 0 | 0
CABINETRY & COUNTERTOPS — Subtotal | 58718 | 0 | 0 | 0 | 58718 | 0 | 0
INTERIOR FINISHING
Finishing Carpentry | 18000 |  |  | 0 | 18000 | 0 | 0
Interior Trim Materials | 13413.68 |  |  | 0 | 13413.68 | 0 | 0
Stair System Materials | 2400 |  |  | 0 | 2400 | 0 | 0
Bathroom Hardware | 500 |  |  | 0 | 500 | 0 | 0
Shower Glass Doors | 6500 |  |  | 0 | 6500 | 0 | 0
Mirrors | 1000 |  |  | 0 | 1000 | 0 | 0
Mantle | 1200 |  |  | 0 | 1200 | 0 | 0
Interior Cedar Beam Wraps/False Beams | 4919.37 |  |  | 0 | 4919.37 | 0 | 0
Shiplap for Electric Fireplace | 1067.6 |  |  | 0 | 1067.6 | 0 | 0
Contingency | 3109.95 |  |  | 0 | 3109.95 | 0 | 0
INTERIOR FINISHING — Subtotal | 52110.6 | 0 | 0 | 0 | 52110.6 | 0 | 0
WOOD FLOOR COVERINGS
Flooring Material - Addition | 7600 |  |  | 0 | 7600 | 0 | 0
Flooring Install Labour - Addition | 5700 |  |  | 0 | 5700 | 0 | 0
Floor Sanding & Prep | 6000 |  |  | 0 | 6000 | 0 | 0
Protective Floor Covering | 500 |  |  | 0 | 500 | 0 | 0
Old Flooring Removal - Existing House | 4800 |  |  | 0 | 4800 | 0 | 0
Flooring Material - Existing House | 9450 |  |  | 0 | 9450 | 0 | 0
Flooring Installation - Existing House | 6750 |  |  | 0 | 6750 | 0 | 0
Contingency | 1980 |  |  | 0 | 1980 | 0 | 0
WOOD FLOOR COVERINGS — Subtotal | 42780 | 0 | 0 | 0 | 42780 | 0 | 0
TILE
Floor Tile Material - Addition | 2532 |  |  | 0 | 2532 | 0 | 0
Floor Tile Install Labour - Addition | 2534 |  |  | 0 | 2534 | 0 | 0
Floor Tile Prep | 1000 |  |  | 0 | 1000 | 0 | 0
Wall Tile Material (Ensuite & Main Bath Shower) | 2726.7 |  |  | 0 | 2726.7 | 0 | 0
Wall Tile Labour (Ensuite & Main Bath Shower) | 4070 |  |  | 0 | 4070 | 0 | 0
Backsplash Tile Material | 400 |  |  | 0 | 400 | 0 | 0
Backsplash Tile Labour | 1200 |  |  | 0 | 1200 | 0 | 0
Heated Floor Prep | 2495.5 |  |  | 0 | 2495.5 | 0 | 0
Thermostats | 610.42 |  |  | 0 | 610.42 | 0 | 0
Ensuite Shower Linear Drain | 1000 |  |  | 0 | 1000 | 0 | 0
Floor Tile Material - Existing House | 3000 |  |  | 0 | 3000 | 0 | 0
Floor Tile Installation - Existing House | 5000 |  |  | 0 | 5000 | 0 | 0
Floor Tile Removal - Existing House | 1200 |  |  | 0 | 1200 | 0 | 0
Contingency | 1806.86 |  |  | 0 | 1806.86 | 0 | 0
TILE — Subtotal | 29575.48 | 0 | 0 | 0 | 29575.48 | 0 | 0
PAINT
Interior Paint | 22000 |  |  | 0 | 22000 | 0 | 0
Exterior Paint | 8500 |  |  | 0 | 8500 | 0 | 0
Door Painting & Staining | 2500 |  |  | 0 | 2500 | 0 | 0
Interior Staining T&G and Beams | 8000 |  |  | 0 | 8000 | 0 | 0
Contingency | 4100 |  |  | 0 | 4100 | 0 | 0
PAINT — Subtotal | 45100 | 0 | 0 | 0 | 45100 | 0 | 0
EXTERIOR HARDSCAPE
Patio Driveway Stone Removal | 5000 |  |  | 0 | 5000 | 0 | 0
New Concrete Driveway to New Garage Bays Material | 8600 |  |  | 0 | 8600 | 0 | 0
New Concrete Driveway Finishing | 4825 |  |  | 0 | 4825 | 0 | 0
Forming Driveway Labour | 3000 |  |  | 0 | 3000 | 0 | 0
EXTERIOR HARDSCAPE — Subtotal | 21425 | 0 | 0 | 0 | 21425 | 0 | 0
CONSTRUCTION CLEAN UP
Clean Up Labour | 10000 |  |  | 0 | 10000 | 0 | 0
Disposal & Dump Fees | 5500 |  |  | 0 | 5500 | 0 | 0
Dumpster Rental | 1500 |  | 233 | 233 | 1267 | 0 | 0
Final Site Clean | 2500 |  |  | 0 | 2500 | 0 | 0
CONSTRUCTION CLEAN UP — Subtotal | 19500 | 0 | 233 | 233 | 19267 | 0 | 0
JOBSITE FACILITIES
Portable Washroom | 1200 | 97.58 | 175 | 272.58 | 927.42 | 0 | 0
Site Signage | 1500 |  |  | 0 | 1500 | 0 | 0
Tool & Rental Equipment | 1000 |  | 309.86 | 309.86 | 690.14 | 0 | 0
Scaffolding | 3500 |  |  | 0 | 3500 | 0 | 0
JOBSITE FACILITIES — Subtotal | 7200 | 97.58 | 484.86 | 582.44 | 6617.56 | 0 | 0
PROJECT MANAGEMENT
Management & Supervision | 25200 | 11736 | 2043.9 | 13779.9 | 11420.1 | 0 | 0
Credit - Management Billing as per Pricing Contract |  | -5000 |  | -5000 | 5000 | 0 | 0
Accounting & Admin | 12600 | 1620 | 810 | 2430 | 10170 | 0 | 0
PROJECT MANAGEMENT — Subtotal | 37800 | 8356 | 2853.9 | 11209.9 | 26590.1 | 0 | 0
MISCELLANEOUS
Travel | 8628.48 | 1172.7 | 737.1 | 1909.8 | 6718.68 | 0 | 0
Deficiencies | 5000 |  | 0 | 0 | 5000 | 0 | 0
Demolition | 23400 |  | 1320.05 | 1320.05 | 22079.95 | 0 | 0
Demolition Dembri removal labour | 2000 |  |  | 0 | 2000 | 0 | 0
MISCELLANEOUS — Subtotal | 39028.48 | 1172.7 | 2057.15 | 3229.85 | 35798.63 | 0 | 0
Project Subtotal | 1172519.65 | 108382.85 | 84098.92 | 192481.77 | 1012338.65 | -9373.68 | 22927.09
15% Mark-up | 175877.9475 | 13875.0405 | 11856.9855 | 25951.2285 | 151850.7975 | -452.97 | 3439.0635
GST (5%) | 67419.8799 | 6112.8945 | 4797.7953 | 10921.6499 | 58209.4724 | -491.3325 | 1318.3077
PROJECT TOTAL | 1415817.4774 | 128370.785 | 100753.7008 | 229354.6484 | 1222398.9199 | -10317.9825 | 27684.4612
COLOUR LEGEND

## Timesheet
LINE ITEM | Date | Name | Billing Status | Duration | Rate | Amount
Project Managment
| 2025-05-06 | Russell McMann | Unbilled | 3 | 90 | 270
| 2025-05-14 | James McMann | Unbilled | 1.5 | 90 | 135
| 2025-05-21 | James McMann | Unbilled | 1.5 | 90 | 135
| 2025-05-30 | James McMann | Unbilled | 4 | 90 | 360
| 2025-06-02 | James McMann | Unbilled | 1.68 | 90 | 151.2
| 2025-06-03 | James McMann | Unbilled | 5.17 | 90 | 465.3
| 2025-06-04 | Abdullah Ibn Alamir | Unbilled | 4 | 90 | 360
| 2025-06-04 | James McMann | Unbilled | 3.33 | 90 | 299.7
| 2025-06-04 | James McMann | Unbilled | 1.67 | 90 | 150.3
| 2025-06-05 | Abdullah Ibn Alamir | Unbilled | 5 | 90 | 450
| 2025-06-05 | James McMann | Unbilled | 2.17 | 90 | 195.3
| 2025-06-16 | Russell McMann | Unbilled | 3 | 90 | 270
| 2025-06-18 | James McMann | Unbilled | 4.5 | 90 | 405
| 2025-06-22 | Abdullah Ibn Alamir | Unbilled | 5.67 | 90 | 510.3
| 2025-06-27 | Abdullah Ibn Alamir | Unbilled | 4.83 | 90 | 434.7
| 2025-06-27 | Kevin Mammen | Unbilled | 3.67 | 90 | 330.3
| 2025-09-25 | James McMann | Unbilled | 3 | 90 | 270
| 2025-10-02 | James McMann | Unbilled | 5.67 | 90 | 510.3
| 2025-10-08 | Russell McMann | Unbilled | 2 | 90 | 180
| 2025-10-09 | Kevin Mammen | Unbilled | 2.67 | 90 | 240.3
| 2025-10-15 | James McMann | Unbilled | 2.33 | 90 | 209.7
| 2025-10-15 | Kevin Mammen | Unbilled | 5.83 | 90 | 524.7
| 2025-10-17 | Kevin Mammen | Unbilled | 1.83 | 90 | 164.7
| 2025-10-22 | James McMann | Unbilled | 2.33 | 90 | 209.7
| 2025-11-13 | James McMann | Unbilled | 2.17 | 90 | 195.3
| 2025-11-18 | Kevin Mammen | Unbilled | 0.33 | 90 | 29.7
| 2025-12-03 | Kevin Mammen | Unbilled | 6.33 | 90 | 569.7
| 2025-12-09 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2025-12-12 | Abdullah Ibn Alamir | Unbilled | 4.5 | 90 | 405
| 2025-12-16 | Kevin Mammen | Unbilled | 3.67 | 90 | 330.3
| 2026-01-21 | Abdullah Ibn Alamir | Unbilled | 0.67 | 90 | 60.3
| 2026-04-17 | James McMann | Unbilled | 3 | 90 | 270
| 2026-04-20 | Russell McMann | Unbilled | 2 | 90 | 180
| 2026-04-20 | James McMann | Unbilled | 2 | 90 | 180
| 2026-04-22 | James McMann | Unbilled | 1.5 | 90 | 135
| 2026-04-28 | James McMann | Unbilled | 2.08 | 90 | 187.2
| 2026-04-29 | James McMann | Unbilled | 2.25 | 90 | 202.5
| 2026-04-30 | James McMann | Unbilled | 1.16 | 90 | 104.4
| 2026-05-04 | James McMann | Unbilled | 1 | 90 | 90
| 2026-05-06 | James McMann | Unbilled | 0.67 | 90 | 60.3
| 2026-05-06 | James McMann | Unbilled | 0.41 | 90 | 36.9
| 2026-05-11 | James McMann | Unbilled | 1.58 | 90 | 142.2
| 2026-05-14 | James McMann | Unbilled | 1.83 | 90 | 164.7
| 2026-05-14 | James McMann | Unbilled | 0.58 | 90 | 52.2
| 2026-05-19 | James McMann | Unbilled | 3.58 | 90 | 322.2
| 2026-05-21 | James McMann | Unbilled | 0.25 | 90 | 22.5
| 2026-05-21 | James McMann | Unbilled | 0.33 | 90 | 29.7
| 2026-05-25 | James McMann | Unbilled | 1.08 | 90 | 97.2
| 2026-05-28 | Russell McMann | Unbilled | 3 | 90 | 270
| 2026-05-28 | James McMann | Unbilled | 2.91 | 90 | 261.9
| 2026-06-02 | James McMann | Unbilled | 0.83 | 90 | 74.7
| 2026-06-03 | James McMann | Unbilled | 2.16 | 90 | 194.4
| 2026-06-04 | James McMann | Unbilled | 1.42 | 90 | 127.8
| 2026-06-08 | James McMann | Unbilled | 2.25 | 90 | 202.5
| 2026-06-08 | James McMann | Unbilled | 0.83 | 90 | 74.7
| 2026-06-09 | James McMann | Unbilled | 1.25 | 90 | 112.5
| 2026-06-11 | James McMann | Unbilled | 0.75 | 90 | 67.5
| 2026-06-11 | James McMann | Unbilled | 0.91 | 90 | 81.9
| 2026-06-16 | James McMann | Unbilled | 1.58 | 90 | 142.2
| 2026-06-17 | James McMann | Unbilled | 0.58 | 90 | 52.2
| 2026-06-18 | James McMann | Unbilled | 1.41 | 90 | 126.9
| 2026-06-19 | James McMann | Unbilled | 1.08 | 90 | 97.2
| 2026-06-22 | James McMann | Unbilled | 0.42 | 90 | 37.8
| 2026-06-22 | James McMann | Unbilled | 2.5 | 90 | 225
| 2026-06-23 | James McMann | Unbilled | 2.66 | 90 | 239.4
| 2026-06-23 | James McMann | Unbilled | 0.25 | 90 | 22.5
| 2026-06-29 | Russell McMann | Unbilled | 1.83 | 90 | 164.7
Total Project Managment |  |  |  | 153.11 |  | 13779.9
Travel Time
| 2026-04-17 | James McMann | Unbilled | 1.33 | 90 | 119.7
| 2026-04-20 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-04-22 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-04-30 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-06 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-11 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-14 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-19 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-21 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-25 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-05-28 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-02 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-03 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-08 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-11 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-18 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-23 | James McMann | Unbilled | 1.17 | 90 | 105.3
| 2026-06-29 | Russell McMann | Unbilled | 1.17 | 90 | 105.3
Total Travel Time |  |  |  | 21.22 |  | 1909.8
Foundation:Slap Prep Labor
| 2026-06-18 | Alaa Kadah | Unbilled | 3.58 | 55 | 196.9
| 2026-06-18 | Fielding K Benton | Unbilled | 7.5 | 55 | 412.5
| 2026-06-24 | Fielding K Benton | Unbilled | 2 | 55 | 110
| 2026-06-26 | Fielding K Benton | Unbilled | 1.58 | 55 | 86.9
Total Foundation:Slap Prep Labor |  |  |  | 14.66 |  | 806.3
Demolition
| 2026-06-23 | Fielding K Benton | Unbilled | 4.33 | 55 | 238.15
| 2026-06-23 | Fielding K Benton | Unbilled | 4.17 | 55 | 229.35
| 2026-06-24 | Fielding K Benton | Unbilled | 0.33 | 55 | 18.15
| 2026-06-24 | Fielding K Benton | Unbilled | 3.08 | 55 | 169.4
Total Demolition |  |  |  | 11.91 |  | 655.05
Total Timesheet |  |  |  | 200.9 |  | 17151.05

## Material
LINE ITEM | Type | Date | Num | Memo | Amount
1047335 B.C. LTD (dba Complete Damp Proof
| Bill | 2026-05-27 | 11561 | 1047335 B.C. LTD (dba Complete Damp Proof Damp proofing 11561 | 2735.6
Total 1047335 B.C. LTD (dba Complete Damp Proof |  |  |  |  | 2735.6
Coastline Plumbing Ltd
| Bill | 2026-06-19 | 3247 | Coastline Plumbing Ltd Radon Piping, Relocation of water service 3247 | 2520.41
Total Coastline Plumbing Ltd |  |  |  |  | 2520.41
DBL Disposal Services Ltd
| Bill | 2026-05-29 | 305329 | DBL Portable Washroom- 305329 | 75
| Bill | 2026-05-31 | 305327 | DBL Disposal Services Ltd Portable Washroom- 305327 | 22.58
| Bill | 2026-06-30 | 307885 | DBL Disposal Services Ltd Portable Washroom- 307885 | 175
| Bill | 2026-06-30 | 316498 | DBL Disposal Services Ltd Disposal Bins 316498 | 233
Total DBL Disposal Services Ltd |  |  |  |  | 505.58
Ecolibrium Energy Solutions Inc.
| Bill | 2025-10-19 | 2344 | Ecolibrium Energy Solutions Inc. Energy Advisor Report 2344 | 975
Total Ecolibrium Energy Solutions Inc. |  |  |  |  | 975
Excel Concrete Finishing Inc
| Bill | 2026-06-30 | 3038 | Excel Concrete Finishing Inc Slab Finishng 3038 | 1440
Total Excel Concrete Finishing Inc |  |  |  |  | 1440
Heidelberg Materials Canada Limited
| Bill | 2026-05-12 | 3190336 | Heidelberg Materials Canada Limited Concrete Footings 3190336 | 6107.56
| Bill | 2026-05-21 | 3191123 | Heidelberg Materials Canada Limited Concrete Walls 3191123 | 7698.65
| Bill | 2026-06-29 | 3194511 | Heidelberg Materials Canada Limited Concrete Skim Coat 3194511 | 2243.79
Total Heidelberg Materials Canada Limited |  |  |  |  | 16050
Island Concrete Pumping Ltd
| Bill | 2026-05-12 | 28435 | Island Concrete Pumping Ltd Concrete Pump Truck 28435 | 1482.88
| Bill | 2026-05-21 | 28478 | Island Concrete Pumping Ltd Concrete Pump Truck 28478 | 1750
Total Island Concrete Pumping Ltd |  |  |  |  | 3232.88
Island Electric Company
| Bill | 2026-04-30 | EWO-1189-1A | Island Electric Company Change Order Underground Cable Replacement 1189-1 | 1864.51
| Bill | 2026-06-15 | EWO-1189-2 | Island Electric Company Change Order Main 400A Service Feeder Cables EWO-1189-2 | 4278
| Bill | 2026-06-15 | EWO-1189-2 | Island Electric Company Change Order Receptacle and Future Lighting Circuit EWO-1189-2 | 960.41
| Bill | 2026-06-15 | EWO-1189-2 | Island Electric Company Change Order Future Swimming Pool Sub-feed EWO-1189-2 | 860.37
| Bill | 2026-06-15 | 1189-1 | Island Electric Company 400A Service Upgrade 1189-1 | 13022
Total Island Electric Company |  |  |  |  | 20985.29
JE Anderson & Associates
| Bill | 2025-11-13 | 0066328 | JE Anderson & Associates Survey 0066328 | 3760.4
| Bill | 2026-02-10 | 0067130 | JE Anderson & Associates Survey 0067130 | 210.75
| Bill | 2026-05-06 | 0067962 | JE Anderson & Associates Survey 0067962 | 892.5
| Bill | 2026-06-08 | 0068312 | JE Anderson & Associates Survey 0068312 | 817
Total JE Anderson & Associates |  |  |  |  | 5680.65
JXN SOLUTIONS LTD
| Bill | 2026-05-28 | invoice 39 | JXN SOLUTIONS LTD Footings and Foundation Labour invoice 39 | 17635
| Bill | 2026-05-28 | invoice 39 | JXN SOLUTIONS LTD Change Order Footings and Foundation Labour invoice 39 | 11431.25
Total JXN SOLUTIONS LTD |  |  |  |  | 29066.25
Kivela Contracting Ltd.
| Bill | 2026-01-16 | 2658 | Kivela Contracting Ltd. Septic Design and Permit 2658 | 1800
| Bill | 2026-04-30 | 2694 | Kivela Contracting Ltd. Site Work 2694 | 7625
| Bill | 2026-04-30 | 2694 | Kivela Contracting Ltd. Change Order Septic Field Work 2694 | 1732.55
| Bill | 2026-06-24 | 2697 | Kivela Contracting Ltd. Site Work 2697 | 26900.55
Total Kivela Contracting Ltd. |  |  |  |  | 38058.1
Kyle Windle
| Bill | 2026-06-30 |  | Kyle Windle Demolition Labour | 665
Total Kyle Windle |  |  |  |  | 665
Lewkowich Engineering Associates Ltd
| Bill | 2025-12-10 | 102800 | Lewkowich Engineering Associates Ltd Geotechnical Assessment Report 102800 | 3760
| Bill | 2026-02-09 | 103557 | Lewkowich Engineering Associates Ltd Geotechnical Assessment Report 103557 | 300
| Bill | 2026-04-10 | 104422 | Lewkowich Engineering Associates Ltd Geotechnical Engineering 104422 | 2477.4
| Bill | 2026-05-11 | 104886 | Lewkowich Engineering Associates Ltd Geotechnical Engineering 104886 | 352.4
| Bill | 2026-06-15 | 105386 | Lewkowich Engineering Associates Ltd Geotech Report 105386 | 130
Total Lewkowich Engineering Associates Ltd |  |  |  |  | 7019.8
Print Three Nanaimo
| Bill | 46128 | 5-36986 | Print Three Nanaimo Revised Plan Printing 5-36986 | 321.75
| Bill | 46147 | 5-37167 | Print Three Nanaimo Plan Printing 5-37167 | 71.16
Total Print Three Nanaimo |  |  |  |  | 392.91
Regional District of Nanaimo
| Bill | 46007 | 2182719713 | Regional District of Nanaimo Building Permit Fees 2182719713 | 1025
| Bill | 46105 | PR20250000587 | Regional District of Nanaimo Building Permit PR20250000587 | 13700.75
| Credit Card Charge | 46149 | 2405438517 | Regional District of Nanaimo BP Revision 2405438517 | 128.13
Total Regional District of Nanaimo |  |  |  |  | 14853.88
Rona 221227- Mcmann Group
| Bill | 46147 | 103-25261351 | Rona Footings and Foundation Material 103-25261351 | 7268.71
| Bill | 46148 | 103-25259301 | Rona Engineering Material 103-25259301 | 637.91
| Bill | 46190 | 103-25311001 | Rona Footings and Foundation Material 103-25311001 | 130.38
| Bill | 46195 | 103-25314501 | Rona Framing Material Cost 103-25314501 | 8.18
| Bill | 46195 | 103-25314711 | Rona Framing Material Cost 103-25314711 | 122.09
| Bill | 46196 | 83323-10489571 | Rona Framing Material Cost 83323-10489571 | 110.65
| Bill | 46202 | 103-25300781 | Rona Framing Material Cost 103-25300781 | 6385.55
| Bill | 46203 | 103-25300782 | Rona Framing Material Cost 103-25300782 | 8469.7
| Bill | 46203 | 103-25300591 | Rona Framing Material Cost 103-25300591 | 4079.43
| Bill | 46203 | 103-25300921 | Rona Framing Material Cost 103-25300921 | 3280.38
Total Rona 221227- Mcmann Group |  |  |  |  | 30492.98
Russel Metals Inc
| Bill | 46182 | 75624994 | Russel Metals Inc Framing Steel Beams 75624994 | 983.06
Total Russel Metals Inc |  |  |  |  | 983.06
Slegg Building Materials
| Bill | 46153 | IN5565137 | Slegg Building Material Footings and Foundation Material IN5565137 | 215.54
| Bill | 46154 | IN5567055 | Slegg Building Material Footings and Foundation Material IN5567055 | 335.43
| Bill | 46156 | IN5570960 | Slegg Building Material Footings and Foundation Material IN5570960 | 207.15
| Bill | 46156 | IN5571123 | Slegg Building Material Footings and Foundation Material IN5571123 | 253.59
| Bill | 46195 | IN3-0043992 | Slegg Building Materials Framing Material Cost IN3-0043992 | 21.76
Total Slegg Building Materials |  |  |  |  | 1033.47
Sunbelt Rentals
| Bill | 46198 | 80009140-0001 | Sunbelt Rental Rental Equipment | 159.86
Total Sunbelt Rentals |  |  |  |  | 159.86
Westcoast Cutting and Coring Ltd.
| Bill | 46183 | 2115166 | Westcoast Cutting and Coring Ltd. Foundation Labour 2115166 | 900
Total Westcoast Cutting and Coring Ltd. |  |  |  |  | 900
Total Vendor Detail |  |  |  |  | 177750.72